## Contents Page
CONTENTS PAGE
South Area - Trim Schedules
1 | Schedules |  |  |  | 2 | Timesheet
| 2017 |  |  |  |  | Timesheet
| JANUARY | FEBRUARY | MARCH | APRIL |  | Timesheet Codes
Timesheet Definitions
| West Run | West Run | West Run | West Run
| Central Run | Central Run | Central Run | Central Run
| East Run | East Run | East Run | East Run
| Blank Month | Blank Month | Blank Month | Blank Month | 3 | Asset information
West Run
| MAY | JUNE | JULY | AUGUST |  | Central Run
East Run
| West Run | West Run | West Run | West Run
| Central Run | Central Run | Central Run | Central Run
| East Run | East Run | East Run | East Run
| Blank Month | Blank Month | Blank Month | Blank Month | 4 | Area/subsection map
| SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
[5 empty] | 5 | Maintenance standard
| West Run | West Run | West Run | West Run
| Central Run | Central Run | Central Run | Central Run
| East Run | East Run | East Run | East Run | 6 | Principles
| Blank Month | Blank Month | Blank Month | Blank Month
[5 empty] | 7 | Definitions

## Jan - West run
| Area: | SOUTH |  | Crew Lead: | Darren Erickson | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
JANUARY 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
1 | 2 |  | 3 |  | 4 | 5 | 6 | 7
New Years Day
|  |  | Cambie Boulevard |  | McCleery Park | Arbutus Park | Fraser River Park
[5 empty] | Maple Grove Park | Riverview Park
[5 empty] | Equipment maintenance | Shannon Park
8 | 9 |  | 10 |  | 11 | 12 | 13 | 14
Buffer day
| William Mackie Park |  | Eburne Park |  |  | Oak Park | Ash Park
| Marpole Park |  | Park site on Shaughnessy St |  |  |  | Cambie Park
| Fraser River Trail Park |  | Ebisu Park
15 | 16 |  | 17 |  | 18 | 19 | 20 | 21
| Oak Meadows Park |  | Cambie Boulevard |  | McCleery Park | Arbutus Park | Fraser River Park
| Montgomery Park |  |  |  | Maple Grove Park | Riverview Park
[5 empty] | Equipment maintenance | Shannon Park
22 | 23 |  | 24 |  | 25 | 26 | 27 | 28
Buffer day
| William Mackie Park |  | Eburne Park |  |  | Oak Park | Ash Park
| Marpole Park |  | Park site on Shaughnessy St |  |  |  | Cambie Park
| Fraser River Trail Park |  | Ebisu Park
29 | 30 |  | 31
| Oak Meadows Park |  | Cambie Boulevard
Montgomery Park

## Jan - Central run
| Area: | SOUTH |  | Crew Lead: | Mike Shaughnessy | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
JANUARY 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
1 | 2 |  | 3 |  | 4 | 5 | 6 | 7
New Years Day
|  |  | Cambie Boulevard |  | Winona Park | Tisdall Park | Columbia Park
[5 empty] | Equipment maintenance |  | MacDonald Park
8 | 9 |  | 10 |  | 11 | 12 | 13 | 14
Buffer day
| Sunset Park |  | Ross Park |  |  | Kingcrest Park | Grays Park
| George Park |  | Moberly Park |  |  |  | Cartier Park
15 | 16 |  | 17 |  | 18 | 19 | 20 | 21
| Hillcrest Park |  | Cambie Boulevard |  | Winona Park | Tisdall Park | Columbia Park
| Riley Park |  |  |  | Equipment maintenance |  | MacDonald Park
22 | 23 |  | 24 |  | 25 | 26 | 27 | 28
Buffer day
| Sunset Park |  | Ross Park |  |  | Kingcrest Park | Grays Park
| George Park |  | Moberly Park |  |  |  | Cartier Park
29 | 30 |  | 31
| Hillcrest Park |  | Cambie Boulevard
Riley Park

## Jan - East run
| Area: | SOUTH |  | Crew Lead: | Frank Ciliberto | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
JANUARY 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
1 | 2 |  | 3 |  | 4 | 5 | 6 | 7
New Years Day
|  |  | Cambie Boulevard |  | Jones Park | Humm Park | Earles Park
[5 empty] | Tecumseh Park | Nanaimo Park | Norquay Park
Equipment maintenance
8 | 9 |  | 10 |  | 11 | 12 | 13 | 14
Buffer day
| Fraserview Park |  | Gordon Park |  |  | Sparwood Park | Champlain Heights Park
| Bobolink Park |  |  |  |  | Captain Cook Park | Kinross Ravine Park
Rosemont Park
15 | 16 |  | 17 |  | 18 | 19 | 20 | 21
| Riverfront Park |  | Cambie Boulevard |  | Jones Park | Humm Park | Earles Park
| Gladstone-Riverside Park |  |  |  | Tecumseh Park | Nanaimo Park | Norquay Park
| East Fraserlands Park North |  |  |  | Equipment maintenance
Everett Crowley Park
22 | 23 |  | 24 |  | 25 | 26 | 27 | 28
Buffer day
| Fraserview Park |  | Gordon Park |  |  | Sparwood Park | Champlain Heights Park
| Bobolink Park |  |  |  |  | Captain Cook Park | Kinross Ravine Park
Rosemont Park
29 | 30 |  | 31
| Riverfront Park |  | Cambie Boulevard
Gladstone-Riverside Park
East Fraserlands Park North
Everett Crowley Park

## Jan - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
JANUARY 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
1 | 2 | 3 |  | 4 | 5 | 6 | 7
New Years Day
8 | 9 | 10 |  | 11 | 12 | 13 | 14
15 | 16 | 17 |  | 18 | 19 | 20 | 21
22 | 23 | 24 |  | 25 | 26 | 27 | 28
29 | 30 | 31

## Feb - West run
| Area: | SOUTH |  | Crew Lead: | Darren Erickson | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
FEBRUARY 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[5 empty] | 1 | 2 | 3 | 4
[5 empty] | McCleery Park | Arbutus Park | Fraser River Park
[5 empty] | Maple Grove Park | Riverview Park
[5 empty] | Equipment maintenance | Shannon Park
5 | 6 |  | 7 |  | 8 | 9 | 10 | 11
Buffer day
| William Mackie Park |  | Eburne Park |  |  | Oak Park | Ash Park
| Marpole Park |  | Park site on Shaughnessy St |  |  |  | Cambie Park
| Fraser River Trail Park |  | Ebisu Park
12 | 13 |  | 14 |  | 15 | 16 | 17 | 18
| Oak Meadows Park |  | Cambie Boulevard |  | McCleery Park | Arbutus Park | Fraser River Park
| Montgomery Park |  |  |  | Maple Grove Park | Riverview Park
[5 empty] | Equipment maintenance | Shannon Park
19 | 20 |  | 21 |  | 22 | 23 | 24 | 25
| Family Day |  |  |  | Buffer day
|  |  | William Mackie Park |  |  | Eburne Park | Oak Park
|  |  | Marpole Park |  |  | Park site on Shaughnessy St
|  |  | Fraser River Trail Park |  |  | Ebisu Park
26 | 27 |  | 28
| Ash Park |  | Oak Meadows Park
| Cambie Park |  | Montgomery Park

## Feb - Central run
| Area: | SOUTH |  | Crew Lead: | Mike Shaughnessy | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
FEBRUARY 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[5 empty] | 1 | 2 | 3 | 4
[5 empty] | Winona Park | Tisdall Park | Columbia Park
[5 empty] | Equipment maintenance |  | MacDonald Park
5 | 6 |  | 7 |  | 8 | 9 | 10 | 11
Buffer day
| Sunset Park |  | Ross Park |  |  | Kingcrest Park | Grays Park
| George Park |  | Moberly Park |  |  |  | Cartier Park
12 | 13 |  | 14 |  | 15 | 16 | 17 | 18
| Hillcrest Park |  | Cambie Boulevard |  | Winona Park | Tisdall Park | Columbia Park
| Riley Park |  |  |  | Equipment maintenance |  | MacDonald Park
19 | 20 |  | 21 |  | 22 | 23 | 24 | 25
| Family Day |  |  |  | Buffer day
|  |  | Sunset Park |  |  | Ross Park | Kingcrest Park
|  |  | George Park |  |  | Moberly Park
26 | 27 |  | 28
| Grays Park |  | Hillcrest Park
| Cartier Park |  | Riley Park

## Feb - East run
| Area: | SOUTH |  | Crew Lead: | Frank Ciliberto | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
FEBRUARY 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[5 empty] | 1 | 2 | 3 | 4
[5 empty] | Jones Park | Humm Park | Earles Park
[5 empty] | Tecumseh Park | Nanaimo Park | Norquay Park
Equipment maintenance
5 | 6 |  | 7 |  | 8 | 9 | 10 | 11
Buffer day
| Fraserview Park |  | Gordon Park |  |  | Sparwood Park | Champlain Heights Park
| Bobolink Park |  |  |  |  | Captain Cook Park | Kinross Ravine Park
Rosemont Park
12 | 13 |  | 14 |  | 15 | 16 | 17 | 18
| Riverfront Park |  | Cambie Boulevard |  | Jones Park | Humm Park | Earles Park
| Gladstone-Riverside Park |  |  |  | Tecumseh Park | Nanaimo Park | Norquay Park
| East Fraserlands Park North |  |  |  | Equipment maintenance
Everett Crowley Park
19 | 20 |  | 21 |  | 22 | 23 | 24 | 25
| Family Day |  |  |  | Buffer day
|  |  | Fraserview Park |  |  | Gordon Park | Sparwood Park
|  |  | Bobolink Park |  |  |  | Captain Cook Park
Rosemont Park
26 | 27 |  | 28
| Champlain Heights Park |  | Riverfront Park
| Kinross Ravine Park |  | Gladstone-Riverside Park
East Fraserlands Park North
Everett Crowley Park

## Feb - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
FEBRUARY 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
|  |  |  | 1 | 2 | 3 | 4
5 | 6 | 7 |  | 8 | 9 | 10 | 11
12 | 13 | 14 |  | 15 | 16 | 17 | 18
19 | 20 | 21 |  | 22 | 23 | 24 | 25
Family Day
26 | 27 | 28

## Mar - West run
| Area: | SOUTH |  | Crew Lead: | Darren Erickson | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
MARCH 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[5 empty] | 1 | 2 | 3 | 4
[5 empty] | Cambie Boulevard | McCleery Park | Arbutus Park
[5 empty] | Equipment maintenance | Maple Grove Park | Riverview Park
Shannon Park
5 | 6 |  | 7 |  | 8 | 9 | 10 | 11
Buffer day
| Fraser River Park |  | William Mackie Park |  |  | Eburne Park | Oak Park
|  |  | Marpole Park |  |  | Park site on Shaughnessy St
|  |  | Fraser River Trail Park |  |  | Ebisu Park
12 | 13 |  | 14 |  | 15 | 16 | 17 | 18
| Ash Park |  | Oak Meadows Park |  | Cambie Boulevard | McCleery Park | Arbutus Park
| Cambie Park |  | Montgomery Park |  | Equipment maintenance | Maple Grove Park | Riverview Park
Shannon Park
19 | 20 |  | 21 |  | 22 | 23 | 24 | 25
Buffer day
| Fraser River Park |  | William Mackie Park |  |  | Eburne Park | Oak Park
|  |  | Marpole Park |  |  | Park site on Shaughnessy St
|  |  | Fraser River Trail Park |  |  | Ebisu Park
26 | 27 |  | 28 |  | 29 | 30 | 31
| Ash Park |  | Oak Meadows Park |  | Cambie Boulevard | McCleery Park | Arbutus Park
| Cambie Park |  | Montgomery Park |  | Equipment maintenance | Maple Grove Park | Riverview Park
Shannon Park

## Mar - Central run
| Area: | SOUTH |  | Crew Lead: | Mike Shaughnessy | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
MARCH 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[5 empty] | 1 | 2 | 3 | 4
[5 empty] | Cambie Boulevard | Winona Park | Tisdall Park
Equipment maintenance
5 | 6 |  | 7 |  | 8 | 9 | 10 | 11
Buffer day
| Columbia Park |  | Sunset Park |  |  | Ross Park | Kingcrest Park
| MacDonald Park |  | George Park |  |  | Moberly Park
12 | 13 |  | 14 |  | 15 | 16 | 17 | 18
| Grays Park |  | Hillcrest Park |  | Cambie Boulevard | Winona Park | Tisdall Park
| Cartier Park |  | Riley Park |  | Equipment maintenance
19 | 20 |  | 21 |  | 22 | 23 | 24 | 25
Buffer day
| Columbia Park |  | Sunset Park |  |  | Ross Park | Kingcrest Park
| MacDonald Park |  | George Park |  |  | Moberly Park
26 | 27 |  | 28 |  | 29 | 30 | 31
| Grays Park |  | Hillcrest Park |  | Cambie Boulevard | Winona Park | Tisdall Park
| Cartier Park |  | Riley Park |  | Equipment maintenance

## Mar - East run
| Area: | SOUTH |  | Crew Lead: | Frank Ciliberto | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
MARCH 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[5 empty] | 1 | 2 | 3 | 4
[5 empty] | Cambie Boulevard | Jones Park | Humm Park
[5 empty] | Equipment maintenance | Tecumseh Park | Nanaimo Park
5 | 6 |  | 7 |  | 8 | 9 | 10 | 11
Buffer day
| Earles Park |  | Fraserview Park |  |  | Gordon Park | Sparwood Park
| Norquay Park |  | Bobolink Park |  |  |  | Captain Cook Park
Rosemont Park
12 | 13 |  | 14 |  | 15 | 16 | 17 | 18
| Champlain Heights Park |  | Riverfront Park |  | Cambie Boulevard | Jones Park | Humm Park
| Kinross Ravine Park |  | Gladstone-Riverside Park |  | Equipment maintenance | Tecumseh Park | Nanaimo Park
East Fraserlands Park North
Everett Crowley Park
19 | 20 |  | 21 |  | 22 | 23 | 24 | 25
Buffer day
| Earles Park |  | Fraserview Park |  |  | Gordon Park | Sparwood Park
| Norquay Park |  | Bobolink Park |  |  |  | Captain Cook Park
Rosemont Park
26 | 27 |  | 28 |  | 29 | 30 | 31
| Champlain Heights Park |  | Riverfront Park |  | Cambie Boulevard | Jones Park | Humm Park
| Kinross Ravine Park |  | Gladstone-Riverside Park |  | Equipment maintenance | Tecumseh Park | Nanaimo Park
East Fraserlands Park North
Everett Crowley Park

## Mar - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
MARCH 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
|  |  |  | 1 | 2 | 3 | 4
5 | 6 | 7 |  | 8 | 9 | 10 | 11
12 | 13 | 14 |  | 15 | 16 | 17 | 18
19 | 20 | 21 |  | 22 | 23 | 24 | 25
26 | 27 | 28 |  | 29 | 30 | 31

## Apr - West run
| Area: | SOUTH |  | Crew Lead: | Darren Erickson | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
APRIL 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
1
2 | 3 |  | 4 |  | 5 | 6 | 7 | 8
Buffer day
| Fraser River Park |  | William Mackie Park |  |  | Eburne Park | Oak Park
|  |  | Marpole Park |  |  | Park site on Shaughnessy St
|  |  | Fraser River Trail Park |  |  | Ebisu Park
9 | 10 |  | 11 |  | 12 | 13 | 14 | 15
Good Friday
| Ash Park |  | Oak Meadows Park |  | Cambie Boulevard | McCleery Park
| Cambie Park |  | Montgomery Park |  | Equipment maintenance | Maple Grove Park
16 | 17 |  | 18 |  | 19 | 20 | 21 | 22
| Easter Monday |  |  |  | Buffer day
|  |  | Arbutus Park |  |  | Fraser River Park | William Mackie Park
|  |  | Riverview Park |  |  |  | Marpole Park
|  |  | Shannon Park |  |  |  | Fraser River Trail Park
23 | 24 |  | 25 |  | 26 | 27 | 28 | 29
| Eburne Park |  | Oak Park |  | Ash Park | Oak Meadows Park | Cambie Boulevard
| Park site on Shaughnessy St |  |  |  | Cambie Park | Montgomery Park
| Ebisu Park |  |  |  | Equipment maintenance

## Apr - Central run
| Area: | SOUTH |  | Crew Lead: | Mike Shaughnessy | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
APRIL 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
1
2 | 3 |  | 4 |  | 5 | 6 | 7 | 8
Buffer day
| Columbia Park |  | Sunset Park |  |  | Ross Park | Kingcrest Park
| MacDonald Park |  | George Park |  |  | Moberly Park
9 | 10 |  | 11 |  | 12 | 13 | 14 | 15
Good Friday
| Grays Park |  | Hillcrest Park |  | Cambie Boulevard | Winona Park
| Cartier Park |  | Riley Park |  | Equipment maintenance
16 | 17 |  | 18 |  | 19 | 20 | 21 | 22
| Easter Monday |  |  |  | Buffer day
|  |  | Tisdall Park |  |  | Columbia Park | Sunset Park
[6 empty] | MacDonald Park | George Park
23 | 24 |  | 25 |  | 26 | 27 | 28 | 29
| Ross Park |  | Kingcrest Park |  | Grays Park | Hillcrest Park | Cambie Boulevard
| Moberly Park |  |  |  | Cartier Park | Riley Park
Equipment maintenance

## Apr - East run
| Area: | SOUTH |  | Crew Lead: | Frank Ciliberto | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
APRIL 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
1
2 | 3 |  | 4 |  | 5 | 6 | 7 | 8
Buffer day
| Earles Park |  | Fraserview Park |  |  | Gordon Park | Sparwood Park
| Norquay Park |  | Bobolink Park |  |  |  | Captain Cook Park
Rosemont Park
9 | 10 |  | 11 |  | 12 | 13 | 14 | 15
Good Friday
| Champlain Heights Park |  | Riverfront Park |  | Cambie Boulevard | Jones Park
| Kinross Ravine Park |  | Gladstone-Riverside Park |  |  | Tecumseh Park
East Fraserlands Park North
Everett Crowley Park
16 | 17 |  | 18 |  | 19 | 20 | 21 | 22
| Easter Monday |  |  |  | Buffer day
|  |  | Humm Park |  |  | Earles Park | Fraserview Park
|  |  | Nanaimo Park |  |  | Norquay Park | Bobolink Park
23 | 24 |  | 25 |  | 26 | 27 | 28 | 29
| Gordon Park |  | Sparwood Park |  | Champlain Heights Park | Riverfront Park | Cambie Boulevard
|  |  | Captain Cook Park |  | Kinross Ravine Park | Gladstone-Riverside Park
|  |  | Rosemont Park |  |  | East Fraserlands Park North
Everett Crowley Park

## Apr - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
APRIL 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
1
2 | 3 | 4 |  | 5 | 6 | 7 | 8
9 | 10 | 11 |  | 12 | 13 | 14 | 15
Good Friday
16 | 17 | 18 |  | 19 | 20 | 21 | 22
Easter Monday
23 | 24 | 25 |  | 26 | 27 | 28 | 29

## May - West run
| Area: | SOUTH |  | Crew Lead: | Darren Erickson | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
MAY 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
| 1 |  | 2 |  | 3 | 4 | 5 | 6
Buffer day
| McCleery Park |  | Arbutus Park |  |  | Fraser River Park | William Mackie Park
| Maple Grove Park |  | Riverview Park |  |  |  | Marpole Park
|  |  | Shannon Park |  |  |  | Fraser River Trail Park
7 | 8 |  | 9 |  | 10 | 11 | 12 | 13
| Eburne Park |  | Oak Park |  | Ash Park | Oak Meadows Park | Cambie Boulevard
| Park site on Shaughnessy St |  |  |  | Cambie Park | Montgomery Park
| Ebisu Park |  |  |  | Equipment maintenance
14 | 15 |  | 16 |  | 17 | 18 | 19 | 20
Buffer day
| McCleery Park |  | Arbutus Park |  |  | Fraser River Park | William Mackie Park
| Maple Grove Park |  | Riverview Park |  |  |  | Marpole Park
|  |  | Shannon Park |  |  |  | Fraser River Trail Park
21 | 22 |  | 23 |  | 24 | 25 | 26 | 27
Victoria Day
|  |  | Eburne Park |  | Oak Park | Ash Park | Oak Meadows Park
|  |  | Park site on Shaughnessy St |  | Equipment maintenance | Cambie Park | Montgomery Park
Ebisu Park
28 | 29 |  | 30 |  | 31
| Cambie Boulevard |  | McCleery Park |  | Arbutus Park
|  |  | Maple Grove Park |  | Riverview Park
Shannon Park
Equipment maintenance

## May - Central run
| Area: | SOUTH |  | Crew Lead: | Mike Shaughnessy | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
MAY 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
| 1 |  | 2 |  | 3 | 4 | 5 | 6
Buffer day
| Winona Park |  | Tisdall Park |  |  | Columbia Park | Sunset Park
[6 empty] | MacDonald Park | George Park
7 | 8 |  | 9 |  | 10 | 11 | 12 | 13
| Ross Park |  | Kingcrest Park |  | Grays Park | Hillcrest Park | Cambie Boulevard
| Moberly Park |  |  |  | Cartier Park | Riley Park
Equipment maintenance
14 | 15 |  | 16 |  | 17 | 18 | 19 | 20
Buffer day
| Winona Park |  | Tisdall Park |  |  | Columbia Park | Sunset Park
[6 empty] | MacDonald Park | George Park
21 | 22 |  | 23 |  | 24 | 25 | 26 | 27
Victoria Day
|  |  | Ross Park |  | Kingcrest Park | Grays Park | Hillcrest Park
|  |  | Moberly Park |  | Equipment maintenance | Cartier Park | Riley Park
28 | 29 |  | 30 |  | 31
| Cambie Boulevard |  | Winona Park |  | Tisdall Park
Equipment maintenance

## May - East run
| Area: | SOUTH |  | Crew Lead: | Frank Ciliberto | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
MAY 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
| 1 |  | 2 |  | 3 | 4 | 5 | 6
Buffer day
| Jones Park |  | Humm Park |  |  | Earles Park | Fraserview Park
| Tecumseh Park |  | Nanaimo Park |  |  | Norquay Park | Bobolink Park
7 | 8 |  | 9 |  | 10 | 11 | 12 | 13
| Gordon Park |  | Sparwood Park |  | Champlain Heights Park | Riverfront Park | Cambie Boulevard
|  |  | Captain Cook Park |  | Kinross Ravine Park | Gladstone-Riverside Park
|  |  | Rosemont Park |  | Equipment maintenance | East Fraserlands Park North
Everett Crowley Park
14 | 15 |  | 16 |  | 17 | 18 | 19 | 20
Buffer day
| Jones Park |  | Humm Park |  |  | Earles Park | Fraserview Park
| Tecumseh Park |  | Nanaimo Park |  |  | Norquay Park | Bobolink Park
21 | 22 |  | 23 |  | 24 | 25 | 26 | 27
Victoria Day
|  |  | Gordon Park |  | Sparwood Park | Champlain Heights Park | Riverfront Park
[5 empty] | Captain Cook Park | Kinross Ravine Park | Gladstone-Riverside Park
[5 empty] | Rosemont Park |  | East Fraserlands Park North
[5 empty] | Equipment maintenance |  | Everett Crowley Park
28 | 29 |  | 30 |  | 31
| Cambie Boulevard |  | Jones Park |  | Humm Park
|  |  | Tecumseh Park |  | Nanaimo Park
Equipment maintenance

## May - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
MAY 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
| 1 | 2 |  | 3 | 4 | 5 | 6
7 | 8 | 9 |  | 10 | 11 | 12 | 13
14 | 15 | 16 |  | 17 | 18 | 19 | 20
21 | 22 | 23 |  | 24 | 25 | 26 | 27
Victoria Day
28 | 29 | 30 |  | 31

## Jun - West run
| Area: | SOUTH |  | Crew Lead: | Darren Erickson | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
JUNE 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[6 empty] | 1 | 2 | 3
[6 empty] | Fraser River Park | William Mackie Park
Marpole Park
Fraser River Trail Park
4 | 5 |  | 6 |  | 7 | 8 | 9 | 10
| Eburne Park |  | Oak Park |  | Ash Park | Oak Meadows Park | Cambie Boulevard
| Park site on Shaughnessy St |  |  |  | Cambie Park | Montgomery Park
| Ebisu Park |  |  |  | Equipment maintenance
11 | 12 |  | 13 |  | 14 | 15 | 16 | 17
Buffer day
| McCleery Park |  | Arbutus Park |  |  | Fraser River Park | William Mackie Park
| Maple Grove Park |  | Riverview Park |  |  |  | Marpole Park
|  |  | Shannon Park |  |  |  | Fraser River Trail Park
18 | 19 |  | 20 |  | 21 | 22 | 23 | 24
| Eburne Park |  | Oak Park |  | Ash Park | Oak Meadows Park | Cambie Boulevard
| Park site on Shaughnessy St |  |  |  | Cambie Park | Montgomery Park
| Ebisu Park |  |  |  | Equipment maintenance
25 | 26 |  | 27 |  | 28 | 29 | 30
Buffer day
| McCleery Park |  | Arbutus Park |  |  | Fraser River Park | William Mackie Park
| Maple Grove Park |  | Riverview Park |  |  |  | Marpole Park
|  |  | Shannon Park |  |  |  | Fraser River Trail Park

## Jun - Central run
| Area: | SOUTH |  | Crew Lead: | Mike Shaughnessy | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
JUNE 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[6 empty] | 1 | 2 | 3
[6 empty] | Columbia Park | Sunset Park
[6 empty] | MacDonald Park | George Park
4 | 5 |  | 6 |  | 7 | 8 | 9 | 10
| Ross Park |  | Kingcrest Park |  | Grays Park | Hillcrest Park | Cambie Boulevard
| Moberly Park |  |  |  | Cartier Park | Riley Park
Equipment maintenance
11 | 12 |  | 13 |  | 14 | 15 | 16 | 17
Buffer day
| Winona Park |  | Tisdall Park |  |  | Columbia Park | Sunset Park
[6 empty] | MacDonald Park | George Park
18 | 19 |  | 20 |  | 21 | 22 | 23 | 24
| Ross Park |  | Kingcrest Park |  | Grays Park | Hillcrest Park | Cambie Boulevard
| Moberly Park |  |  |  | Cartier Park | Riley Park
Equipment maintenance
25 | 26 |  | 27 |  | 28 | 29 | 30
Buffer day
| Winona Park |  | Tisdall Park |  |  | Columbia Park | Sunset Park
[6 empty] | MacDonald Park | George Park

## Jun - East run
| Area: | SOUTH |  | Crew Lead: | Frank Ciliberto | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
JUNE 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[6 empty] | 1 | 2 | 3
[6 empty] | Earles Park | Fraserview Park
[6 empty] | Norquay Park | Bobolink Park
4 | 5 |  | 6 |  | 7 | 8 | 9 | 10
| Gordon Park |  | Sparwood Park |  | Champlain Heights Park | Riverfront Park | Cambie Boulevard
|  |  | Captain Cook Park |  | Kinross Ravine Park | Gladstone-Riverside Park
|  |  | Rosemont Park |  | Equipment maintenance | East Fraserlands Park North
Everett Crowley Park
11 | 12 |  | 13 |  | 14 | 15 | 16 | 17
Buffer day
| Jones Park |  | Humm Park |  |  | Earles Park | Fraserview Park
| Tecumseh Park |  | Nanaimo Park |  |  | Norquay Park | Bobolink Park
18 | 19 |  | 20 |  | 21 | 22 | 23 | 24
| Gordon Park |  | Sparwood Park |  | Champlain Heights Park | Riverfront Park | Cambie Boulevard
|  |  | Captain Cook Park |  | Kinross Ravine Park | Gladstone-Riverside Park
|  |  | Rosemont Park |  | Equipment maintenance | East Fraserlands Park North
Everett Crowley Park
25 | 26 |  | 27 |  | 28 | 29 | 30
Buffer day
| Jones Park |  | Humm Park |  |  | Earles Park | Fraserview Park
| Tecumseh Park |  | Nanaimo Park |  |  | Norquay Park | Bobolink Park

## Jun - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
JUNE 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
[5 empty] | 1 | 2 | 3
4 | 5 | 6 |  | 7 | 8 | 9 | 10
11 | 12 | 13 |  | 14 | 15 | 16 | 17
18 | 19 | 20 |  | 21 | 22 | 23 | 24
25 | 26 | 27 |  | 28 | 29 | 30

## Jul - West run
| Area: | SOUTH |  | Crew Lead: | Darren Erickson | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
JULY 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
2 | 3 |  | 4 |  | 5 | 6 | 7 | 8
Canada Day Stat
|  |  | Eburne Park |  | Oak Park | Ash Park | Oak Meadows Park
|  |  | Park site on Shaughnessy St |  | Equipment maintenance | Cambie Park | Montgomery Park
Ebisu Park
9 | 10 |  | 11 |  | 12 | 13 | 14 | 15
Buffer day
| Cambie Boulevard |  | McCleery Park |  |  | Arbutus Park | Fraser River Park
|  |  | Maple Grove Park |  |  | Riverview Park
Shannon Park
16 | 17 |  | 18 |  | 19 | 20 | 21 | 22
| William Mackie Park |  | Eburne Park |  | Oak Park | Ash Park | Oak Meadows Park
| Marpole Park |  | Park site on Shaughnessy St |  | Equipment maintenance | Cambie Park | Montgomery Park
| Fraser River Trail Park |  | Ebisu Park
23 | 24 |  | 25 |  | 26 | 27 | 28 | 29
Buffer day
| Cambie Boulevard |  | McCleery Park |  |  | Arbutus Park | Fraser River Park
|  |  | Maple Grove Park |  |  | Riverview Park
Shannon Park
30 | 31
William Mackie Park
Marpole Park
Fraser River Trail Park

## Jul - Central run
| Area: | SOUTH |  | Crew Lead: | Mike Shaughnessy | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
JULY 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
2 | 3 |  | 4 |  | 5 | 6 | 7 | 8
Canada Day Stat
|  |  | Ross Park |  | Kingcrest Park | Grays Park | Hillcrest Park
|  |  | Moberly Park |  | Equipment maintenance | Cartier Park | Riley Park
9 | 10 |  | 11 |  | 12 | 13 | 14 | 15
Buffer day
| Cambie Boulevard |  | Winona Park |  |  | Tisdall Park | Columbia Park
MacDonald Park
16 | 17 |  | 18 |  | 19 | 20 | 21 | 22
| Sunset Park |  | Ross Park |  | Kingcrest Park | Grays Park | Hillcrest Park
| George Park |  | Moberly Park |  | Equipment maintenance | Cartier Park | Riley Park
23 | 24 |  | 25 |  | 26 | 27 | 28 | 29
Buffer day
| Cambie Boulevard |  | Winona Park |  |  | Tisdall Park | Columbia Park
MacDonald Park
30 | 31
Sunset Park
George Park

## Jul - East run
| Area: | SOUTH |  | Crew Lead: | Frank Ciliberto | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
JULY 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
2 | 3 |  | 4 |  | 5 | 6 | 7 | 8
Canada Day Stat
|  |  | Gordon Park |  | Sparwood Park | Champlain Heights Park | Riverfront Park
[5 empty] | Captain Cook Park | Kinross Ravine Park | Gladstone-Riverside Park
[5 empty] | Rosemont Park |  | East Fraserlands Park North
[5 empty] | Equipment maintenance |  | Everett Crowley Park
9 | 10 |  | 11 |  | 12 | 13 | 14 | 15
Buffer day
| Cambie Boulevard |  | Jones Park |  |  | Humm Park | Earles Park
|  |  | Tecumseh Park |  |  | Nanaimo Park | Norquay Park
16 | 17 |  | 18 |  | 19 | 20 | 21 | 22
| Fraserview Park |  | Gordon Park |  | Sparwood Park | Champlain Heights Park | Riverfront Park
| Bobolink Park |  |  |  | Captain Cook Park | Kinross Ravine Park | Gladstone-Riverside Park
[5 empty] | Rosemont Park |  | East Fraserlands Park North
[5 empty] | Equipment maintenance |  | Everett Crowley Park
23 | 24 |  | 25 |  | 26 | 27 | 28 | 29
Buffer day
| Cambie Boulevard |  | Jones Park |  |  | Humm Park | Earles Park
|  |  | Tecumseh Park |  |  | Nanaimo Park | Norquay Park
30 | 31
Fraserview Park
Bobolink Park

## Jul - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
JULY 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
2 | 3 | 4 |  | 5 | 6 | 7 | 8
Canada Day Stat
9 | 10 | 11 |  | 12 | 13 | 14 | 15
16 | 17 | 18 |  | 19 | 20 | 21 | 22
23 | 24 | 25 |  | 26 | 27 | 28 | 29
30 | 31

## Aug - West run
| Area: | SOUTH |  | Crew Lead: | Darren Erickson | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
AUGUST 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
|  |  | 1 |  | 2 | 3 | 4 | 5
|  |  | Eburne Park |  | Oak Park | Ash Park | Oak Meadows Park
|  |  | Park site on Shaughnessy St |  | Equipment maintenance | Cambie Park | Montgomery Park
Ebisu Park
6 | 7 |  | 8 |  | 9 | 10 | 11 | 12
| BC Day |  |  |  | Buffer day
|  |  | Cambie Boulevard |  |  | McCleery Park | Arbutus Park
[6 empty] | Maple Grove Park | Riverview Park
Shannon Park
13 | 14 |  | 15 |  | 16 | 17 | 18 | 19
| Fraser River Park |  | William Mackie Park |  | Eburne Park | Oak Park | Ash Park
|  |  | Marpole Park |  | Park site on Shaughnessy St |  | Cambie Park
|  |  | Fraser River Trail Park |  | Ebisu Park
Equipment maintenance
20 | 21 |  | 22 |  | 23 | 24 | 25 | 26
Buffer day
| Oak Meadows Park |  | Cambie Boulevard |  |  | McCleery Park | Arbutus Park
| Montgomery Park |  |  |  |  | Maple Grove Park | Riverview Park
Shannon Park
27 | 28 |  | 29 |  | 30 | 31
| Fraser River Park |  | William Mackie Park |  | Eburne Park | Oak Park
|  |  | Marpole Park |  | Park site on Shaughnessy St
|  |  | Fraser River Trail Park |  | Ebisu Park
Equipment maintenance

## Aug - Central run
| Area: | SOUTH |  | Crew Lead: | Mike Shaughnessy | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
AUGUST 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
|  |  | 1 |  | 2 | 3 | 4 | 5
|  |  | Ross Park |  | Kingcrest Park | Grays Park | Hillcrest Park
|  |  | Moberly Park |  | Equipment maintenance | Cartier Park | Riley Park
6 | 7 |  | 8 |  | 9 | 10 | 11 | 12
| BC Day |  |  |  | Buffer day
|  |  | Cambie Boulevard |  |  | Winona Park | Tisdall Park
13 | 14 |  | 15 |  | 16 | 17 | 18 | 19
| Columbia Park |  | Sunset Park |  | Ross Park | Kingcrest Park | Grays Park
| MacDonald Park |  | George Park |  | Moberly Park |  | Cartier Park
Equipment maintenance
20 | 21 |  | 22 |  | 23 | 24 | 25 | 26
Buffer day
| Hillcrest Park |  | Cambie Boulevard |  |  | Winona Park | Tisdall Park
Riley Park
27 | 28 |  | 29 |  | 30 | 31
| Columbia Park |  | Sunset Park |  | Ross Park | Kingcrest Park
| MacDonald Park |  | George Park |  | Moberly Park
Equipment maintenance

## Aug - East run
| Area: | SOUTH |  | Crew Lead: | Frank Ciliberto | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
AUGUST 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
|  |  | 1 |  | 2 | 3 | 4 | 5
|  |  | Gordon Park |  | Sparwood Park | Champlain Heights Park | Riverfront Park
[5 empty] | Captain Cook Park | Kinross Ravine Park | Gladstone-Riverside Park
[5 empty] | Rosemont Park |  | East Fraserlands Park North
[5 empty] | Equipment maintenance |  | Everett Crowley Park
6 | 7 |  | 8 |  | 9 | 10 | 11 | 12
| BC Day |  |  |  | Buffer day
|  |  | Cambie Boulevard |  |  | Jones Park | Humm Park
[6 empty] | Tecumseh Park | Nanaimo Park
13 | 14 |  | 15 |  | 16 | 17 | 18 | 19
| Earles Park |  | Fraserview Park |  | Gordon Park | Sparwood Park | Champlain Heights Park
| Norquay Park |  | Bobolink Park |  | Equipment maintenance | Captain Cook Park | Kinross Ravine Park
20 | 21 |  | 22 |  | 23 | 24 | 25 | 26
Buffer day
| Riverfront Park |  | Cambie Boulevard |  |  | Jones Park | Humm Park
| Gladstone-Riverside Park |  |  |  |  | Tecumseh Park | Nanaimo Park
Everett Crowley Park
27 | 28 |  | 29 |  | 30 | 31
| Earles Park |  | Fraserview Park |  | Gordon Park | Sparwood Park
| Norquay Park |  | Bobolink Park |  | Equipment maintenance | Captain Cook Park

## Aug - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
AUGUST 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
|  | 1 |  | 2 | 3 | 4 | 5
6 | 7 | 8 |  | 9 | 10 | 11 | 12
BC Day
13 | 14 | 15 |  | 16 | 17 | 18 | 19
20 | 21 | 22 |  | 23 | 24 | 25 | 26
27 | 28 | 29 |  | 30 | 31

## Sept - West run
| Area: | SOUTH |  | Crew Lead: | Darren Erickson | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
SEPTEMBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[7 empty] | 1 | 2
Ash Park
Cambie Park
3 | 4 |  | 5 |  | 6 | 7 | 8 | 9
| Labour Day |  |  |  | Buffer day
|  |  | Oak Meadows Park |  |  | Cambie Boulevard | McCleery Park
|  |  | Montgomery Park |  |  |  | Maple Grove Park
10 | 11 |  | 12 |  | 13 | 14 | 15 | 16
| Arbutus Park |  | Fraser River Park |  | William Mackie Park | Eburne Park | Oak Park
| Riverview Park |  |  |  | Marpole Park | Park site on Shaughnessy St
| Shannon Park |  |  |  | Fraser River Trail Park | Ebisu Park
Equipment maintenance
17 | 18 |  | 19 |  | 20 | 21 | 22 | 23
Buffer day
| Ash Park |  | Oak Meadows Park |  |  | Cambie Boulevard | McCleery Park
| Cambie Park |  | Montgomery Park |  |  |  | Maple Grove Park
24 | 25 |  | 26 |  | 27 | 28 | 29 | 30
| Arbutus Park |  | Fraser River Park |  | William Mackie Park | Eburne Park | Oak Park
| Riverview Park |  |  |  | Marpole Park | Park site on Shaughnessy St
| Shannon Park |  |  |  | Fraser River Trail Park | Ebisu Park
Equipment maintenance

## Sept - Central run
| Area: | SOUTH |  | Crew Lead: | Mike Shaughnessy | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
SEPTEMBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[7 empty] | 1 | 2
Grays Park
Cartier Park
3 | 4 |  | 5 |  | 6 | 7 | 8 | 9
| Labour Day |  |  |  | Buffer day
|  |  | Hillcrest Park |  |  | Cambie Boulevard | Winona Park
Riley Park
10 | 11 |  | 12 |  | 13 | 14 | 15 | 16
| Tisdall Park |  | Columbia Park |  | Sunset Park | Ross Park | Kingcrest Park
|  |  | MacDonald Park |  | George Park | Moberly Park
Equipment maintenance
17 | 18 |  | 19 |  | 20 | 21 | 22 | 23
Buffer day
| Grays Park |  | Hillcrest Park |  |  | Cambie Boulevard | Winona Park
| Cartier Park |  | Riley Park
24 | 25 |  | 26 |  | 27 | 28 | 29 | 30
| Tisdall Park |  | Columbia Park |  | Sunset Park | Ross Park | Kingcrest Park
|  |  | MacDonald Park |  | George Park | Moberly Park
Equipment maintenance

## Sept - East run
| Area: | SOUTH |  | Crew Lead: | Frank Ciliberto | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
SEPTEMBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[7 empty] | 1 | 2
Champlain Heights Park
Kinross Ravine Park
3 | 4 |  | 5 |  | 6 | 7 | 8 | 9
| Labour Day |  |  |  | Buffer day
|  |  | Riverfront Park |  |  | Cambie Boulevard | Jones Park
|  |  | Gladstone-Riverside Park |  |  |  | Tecumseh Park
Everett Crowley Park
10 | 11 |  | 12 |  | 13 | 14 | 15 | 16
| Humm Park |  | Earles Park |  | Fraserview Park | Gordon Park | Sparwood Park
| Nanaimo Park |  | Norquay Park |  | Bobolink Park |  | Captain Cook Park
Equipment maintenance
17 | 18 |  | 19 |  | 20 | 21 | 22 | 23
Buffer day
| Champlain Heights Park |  | Riverfront Park |  |  | Cambie Boulevard | Jones Park
| Kinross Ravine Park |  | Gladstone-Riverside Park |  |  |  | Tecumseh Park
Everett Crowley Park
24 | 25 |  | 26 |  | 27 | 28 | 29 | 30
| Humm Park |  | Earles Park |  | Fraserview Park | Gordon Park | Sparwood Park
| Nanaimo Park |  | Norquay Park |  | Bobolink Park |  | Captain Cook Park
Equipment maintenance

## Sept - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
SEPTEMBER 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
[6 empty] | 1 | 2
3 | 4 | 5 |  | 6 | 7 | 8 | 9
Labour Day
10 | 11 | 12 |  | 13 | 14 | 15 | 16
17 | 18 | 19 |  | 20 | 21 | 22 | 23
24 | 25 | 26 |  | 27 | 28 | 29 | 30

## Oct - West run
| Area: | SOUTH |  | Crew Lead: | Darren Erickson | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
OCTOBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
1 | 2 |  | 3 |  | 4 | 5 | 6 | 7
Buffer day
| Ash Park |  | Oak Meadows Park |  |  | Cambie Boulevard | McCleery Park
| Cambie Park |  | Montgomery Park |  |  |  | Maple Grove Park
8 | 9 |  | 10 |  | 11 | 12 | 13 | 14
Thanksgiving Day
|  |  | Arbutus Park |  | Fraser River Park | William Mackie Park | Eburne Park
|  |  | Riverview Park |  | Equipment maintenance | Marpole Park | Park site on Shaughnessy St
|  |  | Shannon Park |  |  | Fraser River Trail Park | Ebisu Park
15 | 16 |  | 17 |  | 18 | 19 | 20 | 21
Buffer day
| Oak Park |  | Ash Park |  |  | Oak Meadows Park | Cambie Boulevard
|  |  | Cambie Park |  |  | Montgomery Park
22 | 23 |  | 24 |  | 25 | 26 | 27 | 28
| McCleery Park |  | Arbutus Park |  | Fraser River Park | William Mackie Park | Eburne Park
| Maple Grove Park |  | Riverview Park |  | Equipment maintenance | Marpole Park | Park site on Shaughnessy St
|  |  | Shannon Park |  |  | Fraser River Trail Park | Ebisu Park
29 | 30 |  | 31
| Oak Park |  | Ash Park
Cambie Park

## Oct - Central run
| Area: | SOUTH |  | Crew Lead: | Mike Shaughnessy | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
OCTOBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
1 | 2 |  | 3 |  | 4 | 5 | 6 | 7
Buffer day
| Grays Park |  | Hillcrest Park |  |  | Cambie Boulevard | Winona Park
| Cartier Park |  | Riley Park
8 | 9 |  | 10 |  | 11 | 12 | 13 | 14
Thanksgiving Day
|  |  | Tisdall Park |  | Columbia Park | Sunset Park | Ross Park
[5 empty] | MacDonald Park | George Park | Moberly Park
Equipment maintenance
15 | 16 |  | 17 |  | 18 | 19 | 20 | 21
Buffer day
| Kingcrest Park |  | Grays Park |  |  | Hillcrest Park | Cambie Boulevard
|  |  | Cartier Park |  |  | Riley Park
22 | 23 |  | 24 |  | 25 | 26 | 27 | 28
| Winona Park |  | Tisdall Park |  | Columbia Park | Sunset Park | Ross Park
[5 empty] | MacDonald Park | George Park | Moberly Park
Equipment maintenance
29 | 30 |  | 31
| Kingcrest Park |  | Grays Park
Cartier Park

## Oct - East run
| Area: | SOUTH |  | Crew Lead: | Frank Ciliberto | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
OCTOBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
1 | 2 |  | 3 |  | 4 | 5 | 6 | 7
Buffer day
| Champlain Heights Park |  | Riverfront Park |  |  | Cambie Boulevard | Jones Park
| Kinross Ravine Park |  | Gladstone-Riverside Park |  |  |  | Tecumseh Park
Everett Crowley Park
8 | 9 |  | 10 |  | 11 | 12 | 13 | 14
Thanksgiving Day
|  |  | Humm Park |  | Earles Park | Fraserview Park | Gordon Park
|  |  | Nanaimo Park |  | Norquay Park | Bobolink Park
Equipment maintenance
15 | 16 |  | 17 |  | 18 | 19 | 20 | 21
Buffer day
| Sparwood Park |  | Champlain Heights Park |  |  | Riverfront Park | Cambie Boulevard
| Captain Cook Park |  | Kinross Ravine Park |  |  | Gladstone-Riverside Park
Everett Crowley Park
22 | 23 |  | 24 |  | 25 | 26 | 27 | 28
| Jones Park |  | Humm Park |  | Earles Park | Fraserview Park | Gordon Park
| Tecumseh Park |  | Nanaimo Park |  | Norquay Park | Bobolink Park
Equipment maintenance
29 | 30 |  | 31
| Sparwood Park |  | Champlain Heights Park
| Captain Cook Park |  | Kinross Ravine Park

## Oct - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
OCTOBER 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
1 | 2 | 3 |  | 4 | 5 | 6 | 7
8 | 9 | 10 |  | 11 | 12 | 13 | 14
Thanksgiving Day
15 | 16 | 17 |  | 18 | 19 | 20 | 21
22 | 23 | 24 |  | 25 | 26 | 27 | 28
29 | 30 | 31

## Nov - West run
| Area: | SOUTH |  | Crew Lead: | Darren Erickson | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
NOVEMBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[5 empty] | 1 | 2 | 3 | 4
[5 empty] | Buffer day |  |  |  |  | William Mackie Park
[6 empty] | Oak Meadows Park | Cambie Boulevard |  |  | Marpole Park
[6 empty] | Montgomery Park |  |  |  | Fraser River Trail Park
5 | 6 |  | 7 |  | 8 | 9 | 10 | 11
| McCleery Park |  | Arbutus Park |  | Fraser River Park | William Mackie Park | Eburne Park
| Maple Grove Park |  | Riverview Park |  | Equipment maintenance | Marpole Park | Park site on Shaughnessy St
|  |  | Shannon Park |  |  | Fraser River Trail Park | Ebisu Park
12 | 13 |  | 14 |  | 15 | 16 | 17 | 18
| Remembrance Day Stat |  |  |  | Buffer day
|  |  | Oak Park |  |  | Ash Park | Oak Meadows Park
[6 empty] | Cambie Park | Montgomery Park
19 | 20 |  | 21 |  | 22 | 23 | 24 | 25
| Cambie Boulevard |  | McCleery Park |  | Arbutus Park | Fraser River Park | William Mackie Park
|  |  | Maple Grove Park |  | Riverview Park |  | Marpole Park
[5 empty] | Shannon Park |  | Fraser River Trail Park
Equipment maintenance
26 | 27 |  | 28 |  | 29 | 30
Buffer day
| Eburne Park |  | Oak Park |  |  | Ash Park
| Park site on Shaughnessy St |  |  |  |  | Cambie Park
Ebisu Park

## Nov - Central run
| Area: | SOUTH |  | Crew Lead: | Mike Shaughnessy | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
NOVEMBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[5 empty] | 1 | 2 | 3 | 4
Buffer day
[6 empty] | Hillcrest Park | Cambie Boulevard
Riley Park
5 | 6 |  | 7 |  | 8 | 9 | 10 | 11
| Winona Park |  | Tisdall Park |  | Columbia Park | Sunset Park | Ross Park
[5 empty] | MacDonald Park | George Park | Moberly Park
Equipment maintenance
12 | 13 |  | 14 |  | 15 | 16 | 17 | 18
| Remembrance Day Stat |  |  |  | Buffer day
|  |  | Kingcrest Park |  |  | Grays Park | Hillcrest Park
[6 empty] | Cartier Park | Riley Park
19 | 20 |  | 21 |  | 22 | 23 | 24 | 25
| Cambie Boulevard |  | Winona Park |  | Tisdall Park | Columbia Park | Sunset Park
[5 empty] | Equipment maintenance | MacDonald Park | George Park
26 | 27 |  | 28 |  | 29 | 30
Buffer day
| Ross Park |  | Kingcrest Park |  |  | Grays Park
| Moberly Park |  |  |  |  | Cartier Park

## Nov - East run
| Area: | SOUTH |  | Crew Lead: | Frank Ciliberto | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
NOVEMBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[5 empty] | 1 | 2 | 3 | 4
Buffer day
[6 empty] | Riverfront Park | Cambie Boulevard
Gladstone-Riverside Park
Everett Crowley Park
5 | 6 |  | 7 |  | 8 | 9 | 10 | 11
| Jones Park |  | Humm Park |  | Earles Park | Fraserview Park | Gordon Park
| Tecumseh Park |  | Nanaimo Park |  | Norquay Park | Bobolink Park
Equipment maintenance
12 | 13 |  | 14 |  | 15 | 16 | 17 | 18
| Remembrance Day Stat |  |  |  | Buffer day
|  |  | Sparwood Park |  |  | Champlain Heights Park | Riverfront Park
|  |  | Captain Cook Park |  |  | Kinross Ravine Park | Gladstone-Riverside Park
Everett Crowley Park
19 | 20 |  | 21 |  | 22 | 23 | 24 | 25
| Cambie Boulevard |  | Jones Park |  | Humm Park | Earles Park | Fraserview Park
|  |  | Tecumseh Park |  | Nanaimo Park | Norquay Park | Bobolink Park
Equipment maintenance
26 | 27 |  | 28 |  | 29 | 30
Buffer day
| Gordon Park |  | Sparwood Park |  |  | Champlain Heights Park
|  |  | Captain Cook Park |  |  | Kinross Ravine Park

## Nov - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
NOVEMBER 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
|  |  |  | 1 | 2 | 3 | 4
5 | 6 | 7 |  | 8 | 9 | 10 | 11
12 | 13 | 14 |  | 15 | 16 | 17 | 18
Remembrance Day Stat
19 | 20 | 21 |  | 22 | 23 | 24 | 25
26 | 27 | 28 |  | 29 | 30

## Dec - West run
| Area: | SOUTH |  | Crew Lead: | Darren Erickson | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
DECEMBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[7 empty] | 1 | 2
Oak Meadows Park
Montgomery Park
3 | 4 |  | 5 |  | 6 | 7 | 8 | 9
| Cambie Boulevard |  | McCleery Park |  | Arbutus Park | Fraser River Park | Eburne Park
|  |  | Maple Grove Park |  | Riverview Park |  | Park site on Shaughnessy St
[5 empty] | Shannon Park |  | Ebisu Park
Equipment maintenance
10 | 11 |  | 12 |  | 13 | 14 | 15 | 16
Buffer day
| Oak Park |  | Ash Park |  |  | Oak Meadows Park | Cambie Boulevard
|  |  | Cambie Park |  |  | Montgomery Park
17 | 18 |  | 19 |  | 20 | 21 | 22 | 23
| McCleery Park |  | Arbutus Park |  | Fraser River Park | Eburne Park | Oak Park
| Maple Grove Park |  | Riverview Park |  | Equipment maintenance | Park site on Shaughnessy St
|  |  | Shannon Park |  |  | Ebisu Park
24 | 25 |  | 26 |  | 27 | 28 | 29 | 30
| Christmas Day |  | Boxing Day |  | Buffer day
[6 empty] | Ash Park | Oak Meadows Park
[6 empty] | Cambie Park | Montgomery Park
31

## Dec - Central run
| Area: | SOUTH |  | Crew Lead: | Mike Shaughnessy | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
DECEMBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[7 empty] | 1 | 2
Hillcrest Park
Riley Park
3 | 4 |  | 5 |  | 6 | 7 | 8 | 9
| Cambie Boulevard |  | Winona Park |  | Tisdall Park | Columbia Park | Sunset Park
[5 empty] | Equipment maintenance | MacDonald Park | George Park
10 | 11 |  | 12 |  | 13 | 14 | 15 | 16
Buffer day
| Ross Park |  | Kingcrest Park |  |  | Grays Park | Hillcrest Park
| Moberly Park |  |  |  |  | Cartier Park | Riley Park
17 | 18 |  | 19 |  | 20 | 21 | 22 | 23
| Cambie Boulevard |  | Winona Park |  | Tisdall Park | Columbia Park | Sunset Park
[5 empty] | Equipment maintenance | MacDonald Park | George Park
24 | 25 |  | 26 |  | 27 | 28 | 29 | 30
| Christmas Day |  | Boxing Day |  | Buffer day
[6 empty] | Ross Park | Kingcrest Park
Moberly Park
31

## Dec - East run
| Area: | SOUTH |  | Crew Lead: | Frank Ciliberto | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | TRIMMING
DECEMBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[7 empty] | 1 | 2
Riverfront Park
Gladstone-Riverside Park
Everett Crowley Park
3 | 4 |  | 5 |  | 6 | 7 | 8 | 9
| Cambie Boulevard |  | Jones Park |  | Humm Park | Earles Park | Fraserview Park
|  |  | Tecumseh Park |  | Nanaimo Park | Norquay Park | Bobolink Park
Equipment maintenance
10 | 11 |  | 12 |  | 13 | 14 | 15 | 16
Buffer day
| Gordon Park |  | Sparwood Park |  |  | Champlain Heights Park | Riverfront Park
|  |  | Captain Cook Park |  |  | Kinross Ravine Park | Gladstone-Riverside Park
Everett Crowley Park
17 | 18 |  | 19 |  | 20 | 21 | 22 | 23
| Cambie Boulevard |  | Jones Park |  | Humm Park | Earles Park | Fraserview Park
|  |  | Tecumseh Park |  | Nanaimo Park | Norquay Park | Bobolink Park
Equipment maintenance
24 | 25 |  | 26 |  | 27 | 28 | 29 | 30
| Christmas Day |  | Boxing Day |  | Buffer day
[6 empty] | Gordon Park | Sparwood Park
Captain Cook Park
31

## Dec - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
DECEMBER 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
[6 empty] | 1 | 2
3 | 4 | 5 |  | 6 | 7 | 8 | 9
10 | 11 | 12 |  | 13 | 14 | 15 | 16
17 | 18 | 19 |  | 20 | 21 | 22 | 23
24 | 25 | 26 |  | 27 | 28 | 29 | 30
| Christmas Day | Boxing Day
31

## Daily Time Card-South
PARKS OPERATIONS - DAILY TIMESHEET - SOUTH AREA
TIME ENTRY | [7 empty] | WORK RECORD | [5 empty] | Back to Contents
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6
WORKSITE #: |  |  | A) LOCATION:
B) ACTIVITY:
YEAR ____ MONTH ____ DAY ____ |  |  | C) CAUSE (for unfinished work):
D) ORDER #:
INITIAL | PERS. NUMBER | NAME | ACT. TYPE (P#) * | ABS / ATT CODE | PAY SCALE GROUP (GR-) * | LEVEL | PREM# | HOURS | HOURS | HOURS | HOURS | HOURS | HOURS
EQUIP. NUMBER |  | VEHICLE / EQUIPMENT TYPE | [5 empty] | RUN HOURS | RUN HOURS | RUN HOURS | RUN HOURS | RUN HOURS | RUN HOURS
*Please fill in Activity Type & Pay Scale Group ONLY if employee is to be paid HIGHER than their base rate.
X
| Signature - Crew Leader | [7 empty] | Signature - Superintendent
Daily Comments

## Timesheet codes-South
| Code Dictionary |  |  |  |  | Back to Contents
A) Location codes |  | B) Activity codes |  | C) Cause codes
SOUTH |  | TURF |  | WI | Weather interference
|  | MT | Mowing, trimming & leaf mulching | TR | Meetings/training
|  | TF | Turf mainenance / renovation | SA | Sanitation
|  | IR | Irrigation | EV | Events/crowds in park
|  | DM | Diamond maintenance | EB | Equipment breakdown
|  | AM | All weather surface maintenance | EU | Equipment unavailability
|  | ST | Synthetic turf maintenance | SU | Staff unavailability
|  |  |  | HS | Health/safety
|  | HORTICULTURE |  | OM | Other maintenance work
|  | AN | Annual & vegetable bed maintenance
|  | PE | Perennial bed maintenance
|  | RO | Rose bed maintenance
|  | SR | Shrub maintenance (regular & ground cover)
|  | NA | Naturalized maintenance
OTHER
|  | IN | Inspection (Use if no other work was required)
|  | IP | IPM
|  | DR | Debris removal & paperpicking
|  | SN | Snow removal
|  | SD | Storm clean up
|  | BM | Beach maintenance
|  | TM | Tree maintenance
|  | TR | Trail renovation/maintenance
|  | SP | Sport court cleaning
|  | WA | Pond and Water maintenance
|  | EV | Events (eg FOL)
|  | SS | Shipwreck salvage
|  | UF | Urban Forestry
|  | PH | Parking and hard surfaces
|  | AD | Administration
|  | MI | Misc. work
BLOEDEL & SUNSET NURSERY
|  | BC | Bloedel work
|  | NU | Nursery work
CITY-WIDE AREAS
XD | Destination area
XN | North area
XQ | QE, VanDusen, Bloedel, Sunset nursery
XS | South area
XW | West area

## Timesheet Definitions
TIMESHEET TERMS & DEFINITIONS
Back to Contents
MAIN TERMS
LOCATIONS |  | Locations are parks or city contracts where maintenance work is performed by Park Operations on an ongoing basis. Locations worked are tracked daily against staff hours on the timesheet.
ACTIVITIES |  | Activities are regular maintenance work that are tracked daily against staff hours on the timesheets.
CAUSE CODES |  | Cause codes are reasons for an inability to keep on schedule. We’re not measuring the time taken for cause codes, just flagging what contributed to schedule delays in order to identify and remediate these in the future.
EQUIPMENT |  | For the purposes of timesheet completion, only large equipment needs to be filled in. Large equipment includes motorized fleet vehicles, tractors and ride on mowers.
ACTIVITY DESCRIPTIONS
TURF
MT | Mowing, trimming, leaf mulching | Any mowing, trimming, or leaf mulching activity.
TF | Turf maintenance / renovation | Turf maintenance and renovation activities, including, fertilizing, liming (and soil analysis), aerating, top dressing, overseeding, verti cut dethatcher , repairing, edging and fencing.
IR | Irrigation | Any irrigation work including, marking heads, inspections, maintenance and any repairs on irrigation components. This involves both manual and automated systems.
DM | Diamond maintenance | Maintenance work on baseball diamonds, backstops, dugouts, basepads, running pads, and skinned out diamonds. Also includes edging and levelling out low spots. reinstall diamond area turf, sub soil material, irrigation (if applicable), and realign configuration of diamond to spec.
AM | All weather surface maintenance | Any work related to all weather surface fields including the use of a steel float.
SYNTHETIC TURF
ST | Synthetic turf maintenance | Maintenance work on synthetic turf fields including Vac/Blow manual, power sweeping, tow behind blower, weeding, hand grooming, infill topping.
HORTICULTURE
AN | Annual & vegetable bed maintenance | Any work on annual plant displays, including vegetables.
PE | Perennial bed maintenance | Any work on perennials plan display.
RO | Rose maintenance | Any work on formal rose beds .
SR | Shrub maintenance | Any work on shrub beds.
NA | Naturalized maintenance | Work in natural areas (natural state park).
OTHER
IP | IPM | Any work related to integrated pest management monitoring, documenting and control.
IN | Inspection (only used if no other work was required) | Inspect area to determine what, if any, work is required, and how urgent the need is for maintenance/repair.
DR | Debris removal | Paperpicking and collecting garbage/debris on a field or bed.
SN | Snow removal | Snow and ice control.
SD | Storm clean up | Green waste removal, such as broken branches and leaves, following a storm.
BM | Beach maintenance | Maintenance work on beaches.
TM | Tree maintenance | Small tree culture and low branching work on trees.
TR | Trail renovation/maintenance | Maintenance work and repair on trails and pathways, including trail vegetation maintenance.
SP | Sport court cleaning | Cleaning/weeding of hard surface sport courts.
WA | Pond and Water maintenance | Any work on bodies of water, non-chlorinated, non-recreational.
EV | Events (eg. FOL) | Non turf/hort work related to event setup/takedown.
SS | Shipwreck salvage | Removing shipwreck debris.
UF | Urban Forestry | Urban forestry work (Picking up large wood pieces on city streets and parks as a result of tree removal).
PH | Parking and hard surfaces | Maintenance work on parking lots and hard surfaces, including blowing, weeding and sweeping.
AD | Administration | Office work not directly related to a specific maintenance activity.
MI | Misc. work | Any activities that fall outside all other existing activity codes.
BLOEDEL & SUNSET NURSERY
BC | Bloedel work | Work performed at Bloedel Conservatory.
NU | Nursery work | Work performed at Sunset Nursery.
CAUSE CODES
WI | Weather interference | Weather conditions interfering with the timely adherence to the regular maintenance schedule.
TR | Meetings/training | Special meetings or training interfering with the timely adherence to the regular maintenance schedule.
SA | Sanitation | Excessive debris removal or issues with City sanitation services interfering with the timely adherence to the regular maintenance schedule.
EV | Events/crowds in park | Events or crowds of people in parks interfering with the timely adherence to the regular maintenance schedule.
EB | Equipment breakdown | Equipment breakdown interfering with the timely adherence to the regular maintenance schedule.
EU | Equipment unavailability | Equipment not available in your yard or to your crew when it is needed, interfering with the timely adherence to the regular maintenance schedule.
SU | Staff unavailability | Staff absenteeism interfering with the timely adherence to the regular maintenance schedule.
HS | Health/safety | A health concern or a safety risk interfering with the timely adherence to the regular maintenance schedule.
OM | Other maintenance work | Any other maintenance work that was unplanned or not resourced correctly, resulting in an inability to keep to the regular maintenance schedule.

## Maintenance standard
Back to Contents
Trim maintenance standard: Visual criteria
Category | Visual Criteria
Activity | Grass length |  | Root depth |  | Bare ground |  | Weed tolerance |  | Turf health |  | Surface consistency |  | Drainage |  | Cutting height
Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season
Metric | Centimetres |  | Centimetres |  | % of ground cover |  | % of ground cover |  | a) green & healthy b) chlorotic c) heat stressed d) dormant |  | Surface consistency |  | Max. hours to 100% field perculation (no standing water) (once rain stops) |  | Centimetres
Grade A (Soil) | 7 - 8 cm | 7 - 8 cm | 5 - 10 cm | 5 - 10 cm | < 1% | < 1% | < 5% | < 5% | a) green & healthy | a) green & healthy | < 10 cm rise/fall over 5 m | < 10 cm rise/fall over 5 m | 2 hours | 2 hours | 6.5 cm | 6.5 cm
Grade A (Sand) | 7 - 8 cm | 7 - 8 cm | 10 - 15 cm | 10 - 15 cm | < 0.5% | < 0.5% | < 5% | < 5% | a) green & healthy | a) green & healthy | < 10 cm rise/fall over 5 m | < 10 cm rise/fall over 5 m | 1 hour | 1 hour | 6.5 cm | 6.5 cm
Grade B (Regulation, non-irrigated) | 7 - 8 cm | 7 - 8 cm | 5 - 10 cm | 5 - 10 cm | < 1% | < 1% | < 10% | < 10% | a) green & healthy or d) dormant | a) green & healthy or d) dormant | < 10 cm rise/fall over 5 m | < 10 cm rise/fall over 5 m | 2 hours | 2 hours | 6.5 cm | 6.5 cm
Grade C (non-regulation, non-irrigated) | 10 - 12 cm | 10 - 12 cm | n/a | n/a | < 2% | < 2% | < 20% | < 20% | a) green & healthy or d) dormant | a) green & healthy or d) dormant | Surface is easy to mow: No tripping hazards | Surface is easy to mow: No tripping hazards | n/a | n/a | 6.5 cm | 6.5 cm
Meadows | 15 - 60 cm | 15 - 60 cm | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 10 cm | 10 cm
Trim maintenance standard: Maintenance frequency
Category | MOWING |  |  |  | INSPECTION |  |  |  | REPAIR | [5 empty] | PAPER PICK |  | IPM |  | SNOW REMOVAL
Activity | 60-72" ride on mower + line trimming (goal posts) |  | Leaf mulching |  | Vandalism dog hole wear |  | Irrigation |  | Filling holes |  | Wear spots (general field repair) |  | Edging |  | Paper pick |  | IPM |  | Snow removal
Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season
Metric | - |  | - |  | - |  | - |  | - |  | - |  | - |  | - |  | - |  | -
Grade A (Soil) | Every 10 working days | As needed | n/a | As required (weekly) | Inspect and repair weekly |  | Inspect and schedule weekly | n/a | Inspect and repair weekly |  | Inspect and repair weekly |  | n/a | n/a | Twice/week (same schedule as wide area mowing and trimming) |  | As required | As required | n/a | As needed
Grade A (Sand) | Every 10 working days | As needed | n/a | As required (weekly) | Inspect and repair weekly |  | Inspect and schedule weekly | n/a | Inspect and repair weekly |  | Inspect and repair weekly |  | n/a | n/a | Twice/week (same schedule as wide area mowing and trimming) |  | As required | As required | n/a | As needed
Grade B (Regulation, non-irrigated) | Every 10 working days | As needed | n/a | As required (weekly) | Inspect and repair weekly |  | n/a | n/a | Inspect and repair weekly |  | Inspect and repair weekly |  | n/a | n/a | Weekly (same schedule as wide area mowing and trimming) |  | As required | As required | n/a | As needed
Grade C (non-regulation, non-irrigated) | Every 10 working days | As needed | n/a | Every 3 weeks | As required |  | n/a | n/a | As required |  | As required |  | n/a | Once (Sept) | Every 10 working days (same schedule as wide area mowing and trimming) |  | As required | As required | n/a | As needed
Meadows | n/a | n/a | n/a | n/a | As required |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Every 10 working days (same schedule as wide area mowing and trimming) |  | As required | As required | n/a | As needed

## Area map
Back to Contents

## Principles
Back to Contents
Scheduling principles
| 1 | Schedules are future state, using the maintenance standard as the guide and not being constructed by current resource levels.
| 2 | Schedules are on a per park basis.
| 3 | 6 hours of machine run time per day is expected.
| 4 | Where a gap exists between the standard and current resource levels, staff are to be added to crews to bring them from 2 person crews to 3-4 person crews on average.
| 5 | Time for equipment maintenance is built into the schedules, allowing 1.5 hours per week for this work.
| 6 | Equipment maintenance is staggered between areas to allow the mechanic to get to each yard. West on Mondays, Destination on Tuesdays, South on Wednesdays, North on Thursdays.
| 7 | 1 day of buffer is allocated every 10 working days to mitigate equipment breakdowns, weather considerations and other interruptions that may occur, in order to keep crews consistently on schedule.
| 8 | A reactive fly squad exists in the future state to deal with 311 complaints and other reactive issues, to allow park maintenance crews to keep to their schedules.
| 9 | Where multiple crews service the same heritage boulevards, the boulevards are scheduled first to keep the days consistent on which all crews maintain each boulevard.
| 10 | The following crew runs are not scheduled due to their having 2 or less parks under their responsibility: - Destination: Beach run (Auxiliary) - QE, VanDusen, Bloedel

## Definitions
Back to Contents
Park turf types
| 1 | Grade A (soil) | Soil based grass fields. Game fields for sports, or well manicured grass in high profile parks. Irrigated.
| 2 | Grade A (sand) | Sand based grass fields. Game fields for sports, or well manicured grass in high profile parks. Irrigated.
| 3 | Grade B | Soil based grass fields. Practice fields for sports. Non-irrigated.
| 4 | Grade C | Soil based grass areas. Infrequent maintenance. Non-irrigated.
| 5 | Meadows | Unmaintained grass areas. Cut at 4-6 inches in height. Non-irrigated.
| 6 | Synthetic Turf | Synthetic turf fields.
| 7 | Gravel | Gravel fields.
| 8 | Cinder | Legacy running track base.
| 9 | Baseball Diamond (pads) | Diamond with all grass infields.
| 10 | Baseball Diamond | Diamond with grass infield and gravel base paths.
| 11 | Softball Diamond | Diamond with all gravel infields (softball).
| Category |  | Maintenance Activity | Maintenance Activity Description
| 1 | Mowing | Wide area Mower | Ride on Mower that cuts larger areas, including sports fields and passive areas. Up to 16' wide.
|  |  | 60-72" ride on mower | Small ride on mower that is towed on a trailer or independently operated from park to park. Used for smaller areas to cut grass that is not accessible by the big mower. Often follows the wide area mower as a clean up crew.
|  |  | Trimming | Manual operation of the line trimmer/hand mower to cut grass along sidewalk edges, around benches and trees and anywhere else the mower can't get close enough to.
|  |  | Leaf Mulching | Mulching of leaves in parks where volumes are light enough to allow mulching without being detrimental to turf growth or unsightly. This operation is done by all grass mowers.
| 2 | Turf Amendment | Fertilizing | Fertilization of sports fields and premier turf to maintain proper growth of plant material. Applications vary on what the growing median is, sand or soil, and ranges from 2 - 5 times per year.
|  |  | Lime (and soil analysis) | Liming occurs after a soil analysis is done. Lime is used to adjust the pH of the soil in order for nutrients from fertilization to be available to the grass plant. Application rates are specific depending on how much the pH needs to be changed.
|  |  | Aeration: Rapid Core/core harvest | The rapid core, a 3 point attachment on a tractor, punches out small pieces of the thatch layer to allow better flow of nutrients and water to penetrate the surface and be available to the plant. The holes are punched at a very high frequency, every 3-4 ". The thatch cores are then collected by the core harvester that is a tow behind attached to a tractor. This is done to prevent a layer of thatch to develop causing the turf to be weak and water logged. Used on sand based fields where compaction is not an issue. Sand is added by topdressing, as in the vertidrain process and then dragged. The dragging also fills in low areas of the field to create a smoother, safer playing surface.
|  |  | Aeration: Vertidrain | This unit is a 3 point attachment on a tractor that is used to aerate soil based fields where compaction and poor drainage is an issue. This process is usually used in conjunction with a topdressing of sand, applied by a tractor pulling a sand spreader. This is done to create columns of sand thus increasing the movement of air, water and fertilizer in to the root zone. These fields are dragged with a drag mat pulled by a tractor to increase the efficiency of getting the sand into the columns. The dragging also fills in low areas of the field to create a smoother, safer playing surface.
|  |  | Aeration: Tow Behind | Used to aerate passive areas and B Fields. Towed behind a tractor. Used as a quick process to get to areas not normally aerated through other means. Helps reduce compaction and allows for increased drainage. Encourages healthy growth.
|  |  | Top Dress | This unit is a tow behind by a tractor. It is used to spread sand on a field during the aeration process. The sand fills the opening made by the aerator, thus increasing nutrient and water flow creating healthier turf. Once dragged in it also helps level the playing surface.
|  |  | Overseed | Unit is a 3-point attachment for a tractor. It cuts grooves into the surface and deposits seed onto the playing field. The overseeding process helps fill in bare patches, and has turf grow into areas with winter damage, and high damaged surfaces.
|  |  | Irrigation | The intentional controlled application of water to turf to promote a healthy, vigorous, sustainable stand of turf. This involves marking heads, inspections, maintenance and any repairs on irrigation components. This involves both manual and automated systems.
|  |  | Verti cut dethatch weed control | This process uses a tow behind unit for a tractor. Process is used to control thatch and weeds in turf areas. Decreasing thatch allows for a healthier turf and better water and nutrient availability. This is important because we do not use herbicides to control weeds.
| 3 | Inspection | Vandalism dog hole wear | Inspections on a weekly basis to ensure safety of the field and update field status page on the City Website. Regular inspections to complete repairs as necessary. This also applies to vehicle damage and tire ruts.
| 4 | Repair | Filling Holes | This repair work is identified through regular inspections. Examples are dog damage, field usage, and vehicular vandalism/damage.
|  |  | Wear Spots | Replacing turf surface on damaged areas to maintain consistent surface either by seeding or returfing.
|  |  | Edging | Any edging required in a park. This is done around any hard surface that grass encroaches upon. Examples: Benches, sidewalks, picnic table, and litter carts.
| 5 | Paper Pick | Debris removal | Picking up of garbage/debris on a field. Debris removal is done before any maintenance on a field. This prevents garbage from being shredded and dispersed through-out the area.
| 6 | Grooming (synthetic turf) | Vac/ Blow manual | Blowing of sidewalks and synthetic turf areas completed by backpack blowers. This is also for blowing leaves and grass clippings off hard surfaces to prevent slipping hazards, keep organic debris off the field, as well as to create a groomed appearance.
|  |  | Vac/Blow (power sweeping) | Unit is a tow behind for tractor. Grooms, vaccuums debris, and loosens infill to restore the carpet pile. (Infill Grooming Machine)
|  |  | Blower | Tow behind unit, For blowing leaves and small debris from field surface.
|  |  | Weed Control (Weeding & Moss removal) | Prong rake is used to weed at the interface between the synthetic grass and the perimeter curb. If necessary, biodegradable weed killer is used to treat the area.
|  |  | Groom Machine (Brush Sweeper) | Tow behind 3 point hitch attached brush with rows of tine brush used to agitate exposed fibres and to groom top layer of the infill. This process prevents the exposed grass fibers from matting down and loosens infill to optimize drainage. (Every six weeks).
|  |  | Groom Hand | Hand groomer (walk-behind) does edges that large machines can't get to. The groomer contains a magnet to pick up metallic objects, filter biological debris, agitate exposed fibres and groom the top layer of the infill. This process prevents the exposed grass fibers from matting down and loosens infill to optimize drainage.
|  |  | Infill Topping | This process uses a manual stiff bristle brush and garden rake to agitate the exposed fibers. Pre-mixed infill is then applied and distributed evenly over the area.
|  |  | Power Sweeper | Tow behind power-take-off-driven unit, combs the turf surface in order to remove debris such as sunflower seeds, metal, loose debris and other organic debris. The unit is equipped with tines, brush, vacuum, magnetic roller and a mesh for screening and separating rubber infill and dropping the infill back down into the carpet.
| 7 | Grooming | Pre-Season Diamond Preparation | Physically remove all weeds from aggregate around backstops, dugouts, basepads, running pads, and skinned out diamonds. Also includes edging and levelling out low spots.
| 8 | All weather surface | Re-grade (all weather surface) | Use of a steel float that is towed/dragged behind a tractor or truck. This unit levels, grades, and reduces weed growth.
| 9 | Re-Build | Diamond Re-Build | Tear out existing diamond, reinstall diamond area turf, sub soil material, irrigation (if applicable), and realign configuration of diamond to spec.
| 10 | IPM | IPM | A systematic controlled approach that utilizes a variety of least disruptive techniques in order to reduce pest damage or unwanted vegetation to thresholds of tolerable levels. Methods include a combination of physical, cultural, biological and chemical methods chosen for the most effective, safe and economical control of pests and diseases. Synthetic pesticides should be used as a last resort.

## Asset Info - West run
Back to Contents
Park asset information
| A + PN + A + T + XX = asset ID reference |  | Area: | SOUTH
| Area | (A) | Section: | WEST RUN
| Park name | (PN) | Crew type: | TRIM
| Asset | (A)
| Type | (T)
| Sequential number | (XX)
| Location | Park Code | Asset ID(s) | Grade A (Soil) | Grade A (Sand) | Grade B f | Grade C f
| McCleery Park | MC | SMCTC01 | - | - | - | 3736.9649
| Maple Grove Park | MV | SMVTA01 | 998.2884 | - | - | -
|  | MV | SMVTB01 | - | - | 3589.9167 | -
|  | MV | SMVTC01 | - | - | - | 32079.6585
| Arbutus Park | AR | SARTC01 | - | - | - | 9126.8291
| Riverview Park | RV | SRVTC01 | - | - | - | 24528.2667
| Shannon Park | SH | SSHTA01 | 7147.0709 | - | - | -
|  | SH | SSHTC01 | - | - | - | 3333.9101
| William Mackie Park | WI | SWITC01 | - | - | - | 3053.5486
| Marpole Park | MR | SMRTC01 | - | - | - | 2714.8305
| Fraser River Trail Park (Hudson Walkway) | FT | SFTTC01 | - | - | - | ?
| Ebisu Park | EI | SEITC01 | - | - | - | 2998.8977
| Eburne Park | EU | SEUTC01 | - | - | - | 7274.5566
| Park Site on Shaughnessy St. | PH | SPHTC01 | - | - | - | 3766.8846
| Montgomery Park | MM | SMMTA01 | 19836.6784 | - | - | -
|  | MM | SMMTB01 | - | - | 17388.9204 | -
|  | MM | SMMTC01 | - | - | - | 5737.1781
| Oak Meadows Park | OM | SOMTA01 | - | 9460.3865 | - | -
|  | OM | SOMTC01 | - | - | - | 29345.5349
| Fraser River Park | FR | SFRTB01 | - | - | 6884.2835 | -
|  | FR | SFRTC01 | - | - | - | 36971
| Cambie Park | CM | SCMTC01 | - | - | - | 10465.0844
| Oak Park | OA | SOATB01 | - | - | 15552.5769 | -
|  | OA | SOATC01 | - | - | - | 20459.1287
| Ash Park | AS | SASTC01 | - | - | - | 4965.0721
| Cambie Boulevard (49th to Marine Dr.) | XC | BXCTC01 | - | - | - | 44379
|  | Totals: | - | 27982.0377 | 9460.3865 | 43415.6976 | 244936.3454

## Asset Info - Central run
Back to Contents
Park asset information
| A + PN + A + T + XX = asset ID reference |  | Area: | SOUTH
| Area | (A) | Section: | CENTRAL RUN
| Park name | (PN) | Crew type: | TRIM
| Asset | (A)
| Type | (T)
| Sequential number | (XX)
| Location | Park Code | Asset ID(s) | Grade A (Soil) | Grade A (Sand) | Grade B f | Grade C f
| Cartier Park | CT | SCTTC01 | - | - | - | 3383
| Columbia Park | CZ | SCZTB01 | - | - | 16573.8342 | -
|  | CZ | SCZTC01 | - | - | - | 10204.38
| George Park | GE | SGETC01 | - | - | - | 15190.1359
| Grays Park | GY | SGYTC01 | - | - | - | 11170.6016
| Hillcrest Park | HP | SHPTA01 | - | 38618.1738 | - | -
|  | HP | SHPTC01 | - | - | - | 51423.3217
| Kingcrest Park | KN | SKNTA01 | 7936 | - | - | -
|  | KN | SKNTC01 | - | - | - | 15029.8909
| MacDonald Park | MD | SMDTC01 | - | - | - | 9942.4787
| Moberly Park | MO | SMOTA01 | 16554.2998 | - | - | -
|  | MO | SMOTC01 | - | - | - | 18558.5532
| Riley Park | RI | SRITB01 | - | - | 4075.2801 | -
|  | RI | SRITC01 | - | - | - | 7240.9488
| Ross Park | RS | SRSTB01 | - | - | 6772.01 | -
|  | RS | SRSTC01 | - | - | - | 8340.9068
| Sunset Park | SE | SSETB01 | - | - | 10064.8967 | -
|  | SE | SSETC01 | - | - | - | 26190.03
| Tisdall Park | TI | STITA01 | 16267.7579 | - | - | -
|  | TI | STITC01 | - | - | - | 30359.3489
| Winona Park | WN | SWNTA01 | 26402.2508 | - | - | -
|  | WN | SWNTC01 | - | - | - | 29322.1131
| Cambie Boulevard (49th to 33rd) | XC | BXCTC01 | - | - | - | 44379
|  | Totals: | - | 67160.3085 | 38618.1738 | 37486.021 | 280734.7097

## Asset Info - East run
Back to Contents
Park asset information
| A + PN + A + T + XX = asset ID reference |  | Area: | SOUTH
| Area | (A) | Section: | EAST RUN
| Park name | (PN) | Crew type: | TRIM
| Asset | (A)
| Type | (T)
| Sequential number | (XX)
| Location | Park Code | Asset ID(s) | Grade A (Soil) | Grade A (Sand) | Grade B f | Grade C f
| Bobolink Park | BO | SBOTA01 | 15494.9694 | - | - | -
|  | BO | SBOTB01 | - | - | 2851.8646 | -
|  | BO | SBOTC01 | - | - | - | 16727.5242
| Captain Cook Park | CC | SCCTC01 | - | - | - | 16514.0232
| Earles Park | EA | SEATB01 | - | - | 5806.1632 | -
|  | EA | SEATC01 | - | - | - | 10662.639
| East Fraserlands Neighbourhood Park North (Pierview Crescent Park) | EF | SEFTA01 | 111.8516 | - | - | -
| Everett Crowley Park | EV | SEVTC01 | - | - | - | 5448
| Fraserview Park | FV | SFVTB01 | - | - | 2164.3072 | -
|  | FV | SFVTC01 | - | - | - | 5801.3619
| Gladstone-Riverside Park | GR | SGRTC01 | - | - | - | 717.5421
| Gordon Park | GO | SGOTB01 | - | - | 43666.2304 | -
|  | GO | SGOTC01 | - | - | - | 18656.4843
| Humm Park | HU | SHUTC01 | - | - | - | 2616.5117
| Jones Park | JO | SJOTB01 | - | - | 4007.0682 | -
|  | JO | SJOTC01 | - | - | - | 7810.0536
| Kinross Ravine Park | KR | SKRTC01 | - | - | - | ?
| Nanaimo Park | NA | SNATB01 | - | - | 12521.7817 | -
|  | NA | SNATC01 | - | - | - | 13203.4088
| Norquay Park | NO | SNOTB01 | - | - | 8829.6459 | -
|  | NO | SNOTC01 | - | - | - | 11538.7179
| Rosemont Park | RM | SRMTC01 | - | - | - | 4915.7099
| Sparwood Park | SW | SSWTB01 | - | - | 4966.6996 | -
|  | SW | SSWTC01 | - | - | - | 25830.368
| Tecumseh Park | TE | STETC01 | - | - | - | 18547.1401
| Cambie Boulevard (33rd 25th) | XC | BXCTC01 | - | - | - | 44379
|  | Totals: | - | 15606.8211 | - | 84813.7607 | 203368.4846