## Contents Page
CONTENTS PAGE
South Area - WAM Schedules
1 | Schedules |  |  |  | 2 | Timesheet
| 2017 |  |  |  |  | Timesheet
| APRIL | MAY | JUNE | JULY |  | Timesheet Codes
Timesheet Definitions
| West Run | West Run | West Run | West Run
| Central Run | Central Run | Central Run | Central Run
| East Run | East Run | East Run | East Run
| Blank Month | Blank Month | Blank Month | Blank Month | 3 | Asset information
West Run
| AUGUST | SEPTEMBER | OCTOBER | NOVEMBER |  | Central Run
East Run
| West Run | West Run | West Run | West Run
| Central Run | Central Run | Central Run | Central Run
| East Run | East Run | East Run | East Run
| Blank Month | Blank Month | Blank Month | Blank Month | 4 | Area/subsection map
DECEMBER
[5 empty] | 5 | Maintenance standard
West Run
Central Run
| East Run |  |  |  | 6 | Principles
Blank Month
[5 empty] | 7 | Definitions

## Apr - West run
| Area: | SOUTH |  | Crew Lead: | Coleton Fee | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
APRIL 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
1
2 | 3 |  | 4 |  | 5 | 6 | 7 | 8
| McCleery Park (C) |  | Shannon Park (A) |  | Buffer day | Maple Grove Park (B+C) | Shannon Park (A)
| Arbutus Park (C) |  | Tisdall Park (A) |  |  | Oak Park (B) | Tisdall Park (A)
| Fraser River Park (C) |  | Winona Park (A) |  |  | Columbia Park (B+C) | Winona Park (A)
| Shannon Park (C) |  | Oak Meadows (A) |  |  |  | Oak Meadows (A)
|  |  | Montgomery Park (A+B) |  |  |  | Montgomery Park (A+B)
Mechanic day
9 | 10 |  | 11 |  | 12 | 13 | 14 | 15
| Eburne Park (C) |  | Shannon Park (A) |  | Maple Grove Park (B+C) | Shannon Park (A) | Good Friday
| Ash Park (C) |  | Tisdall Park (A) |  | Oak Park (B) | Tisdall Park (A)
| Cambie Park (C) |  | Winona Park (A) |  | Columbia Park (B+C) | Winona Park (A)
| Marpole Park (C) |  | Oak Meadows (A) |  | Mechanic day | Oak Meadows (A)
| Winona Park (C) |  | Montgomery Park (A+B) |  |  | Montgomery Park (A+B)
Tisdall Park (C)
16 | 17 |  | 18 |  | 19 | 20 | 21 | 22
| Easter Monday |  | McCleery Park (C) |  | Buffer day | Maple Grove Park (B+C) | Shannon Park (A)
|  |  | Arbutus Park (C) |  |  | Oak Park (B) | Tisdall Park (A)
|  |  | Fraser River Park (C) |  |  | Columbia Park (B+C) | Winona Park (A)
|  |  | Shannon Park (C) |  |  |  | Oak Meadows (A)
Montgomery Park (A+B)
Mechanic day
23 | 24 |  | 25 |  | 26 | 27 | 28 | 29
| Eburne Park (C) |  | Shannon Park (A) |  | McCleery Park (C) | Maple Grove Park (B+C) | Shannon Park (A)
| Ash Park (C) |  | Tisdall Park (A) |  | Arbutus Park (C) | Oak Park (B) | Tisdall Park (A)
| Cambie Park (C) |  | Winona Park (A) |  | Fraser River Park (C) | Columbia Park (B+C) | Winona Park (A)
| Marpole Park (C) |  | Oak Meadows (A) |  | Shannon Park (C) |  | Oak Meadows (A)
| Winona Park (C) |  | Montgomery Park (A+B) |  | Mechanic day |  | Montgomery Park (A+B)
Tisdall Park (C)

## Apr - Central run
| Area: | SOUTH |  | Crew Lead: | Lorri Lawson | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
APRIL 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
1
2 | 3 |  | 4 |  | 5 | 6 | 7 | 8
| Riley Park (C) |  | Hillcrest (A) |  | Buffer day | Gordon Park (B) | Hillcrest (A)
| Hillcrest Park (C) |  | Memorial South Park (A) |  |  | Riley Park (B) | Memorial South Park (A)
| Cartier Park (C) |  | Moberly Park (A) |  |  | George Park (B) | Moberly Park (A)
| Grays Park (C) |  |  |  |  | Ross Park (B)
Macdonald Park (C)
| Sunset Park (C) |  |  |  | Mechanic day
Tecumseh Park (C)
9 | 10 |  | 11 |  | 12 | 13 | 14 | 15
| Memorial South Park (C) |  | Hillcrest (A) |  | Gordon Park (B) | Hillcrest (A) | Good Friday
| Gordon Park (C) |  | Memorial South Park (A) |  | Riley Park (B) | Memorial South Park (A)
| Ross Park (C) |  | Moberly Park (A) |  | George Park (B) | Moberly Park (A)
| Moberly Park (C) |  |  |  | Ross Park (B)
| Fraserview Park (C) |  |  |  | Mechanic day
16 | 17 |  | 18 |  | 19 | 20 | 21 | 22
| Easter Monday |  | Hillcrest (A) |  | Buffer day | Gordon Park (B) | Hillcrest (A)
|  |  | Memorial South Park (A) |  |  | Riley Park (B) | Memorial South Park (A)
|  |  | Moberly Park (A) |  |  | George Park (B) | Moberly Park (A)
Ross Park (B)
Mechanic day
23 | 24 |  | 25 |  | 26 | 27 | 28 | 29
| Riley Park (C) |  | Hillcrest (A) |  | Memorial South Park (C) | Gordon Park (B) | Hillcrest (A)
| Hillcrest Park (C) |  | Memorial South Park (A) |  | Gordon Park (C) | Riley Park (B) | Memorial South Park (A)
| Cartier Park (C) |  | Moberly Park (A) |  | Ross Park (C) | George Park (B) | Moberly Park (A)
| Grays Park (C) |  |  |  | Moberly Park (C) | Ross Park (B)
| Macdonald Park (C) |  |  |  | Fraserview Park (C)
| Sunset Park (C) |  |  |  | Mechanic day
Tecumseh Park (C)

## Apr - East run
| Area: | SOUTH |  | Crew Lead: | Tony Brown | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
APRIL 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
1
2 | 3 |  | 4 |  | 5 | 6 | 7 | 8
| Sparwood Park (C) |  | Bobolink Park (A) |  | Buffer day | Jones Park (B) | Bobolink Park (A)
| Captain Cook Park (C) |  | Champlain Park (A) |  |  | Earles Park (B) | Champlain Park (A)
| Rosemont Park (C) |  | Killarney Park (A) |  |  | Norquay Park (B+C) | Killarney Park (A)
| Humm Park (C) |  | Kingcrest Park (A) |  |  | Nanaimo Park (B+C) | Kingcrest Park (A)
| Riverfront Park (C) |  | Kensington Park (A) |  |  |  | Kensington Park (A)
| Champlain Park (C) |  |  |  | Mechanic day
Killarney Park (C)
9 | 10 |  | 11 |  | 12 | 13 | 14 | 15
| Kingcrest Park (C) |  | Bobolink Park (A) |  | Jones Park (B) | Bobolink Park (A) | Good Friday
| Kensington Park (C) |  | Champlain Park (A) |  | Earles Park (B) | Champlain Park (A)
| Jones Park (C) |  | Killarney Park (A) |  | Norquay Park (B+C) | Killarney Park (A)
| Earles Park (C) |  | Kingcrest Park (A) |  | Nanaimo Park (B+C) | Kingcrest Park (A)
| Killarney Park (C) |  | Kensington Park (A) |  | Mechanic day | Kensington Park (A)
16 | 17 |  | 18 |  | 19 | 20 | 21 | 22
| Easter Monday |  | Bobolink Park (A) |  | Buffer day | Jones Park (B) | Bobolink Park (A)
|  |  | Champlain Park (A) |  |  | Earles Park (B) | Champlain Park (A)
|  |  | Killarney Park (A) |  |  | Norquay Park (B+C) | Killarney Park (A)
|  |  | Kingcrest Park (A) |  |  | Nanaimo Park (B+C) | Kingcrest Park (A)
|  |  | Kensington Park (A) |  |  |  | Kensington Park (A)
Mechanic day
23 | 24 |  | 25 |  | 26 | 27 | 28 | 29
| Sparwood Park (C) |  | Bobolink Park (A) |  | Kingcrest Park (C) | Jones Park (B) | Bobolink Park (A)
| Captain Cook Park (C) |  | Champlain Park (A) |  | Kensington Park (C) | Earles Park (B) | Champlain Park (A)
| Rosemont Park (C) |  | Killarney Park (A) |  | Jones Park (C) | Norquay Park (B+C) | Killarney Park (A)
| Humm Park (C) |  | Kingcrest Park (A) |  | Earles Park (C) | Nanaimo Park (B+C) | Kingcrest Park (A)
| Riverfront Park (C) |  | Kensington Park (A) |  | Killarney Park (C) |  | Kensington Park (A)
| Champlain Park (C) |  |  |  | Mechanic day
Killarney Park (C)

## Apr - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
APRIL 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
1
2 | 3 | 4 |  | 5 | 6 | 7 | 8
9 | 10 | 11 |  | 12 | 13 | 14 | 15
Good Friday
16 | 17 | 18 |  | 19 | 20 | 21 | 22
Easter Monday
23 | 24 | 25 |  | 26 | 27 | 28 | 29

## May - West run
| Area: | SOUTH |  | Crew Lead: | Coleton Fee | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
MAY 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
| 1 |  | 2 |  | 3 | 4 | 5 | 6
| Eburne Park (C) |  | Shannon Park (A) |  | Buffer day | Maple Grove Park (B+C) | Shannon Park (A)
| Ash Park (C) |  | Tisdall Park (A) |  |  | Oak Park (B) | Tisdall Park (A)
| Cambie Park (C) |  | Winona Park (A) |  |  | Columbia Park (B+C) | Winona Park (A)
| Marpole Park (C) |  | Oak Meadows (A) |  |  |  | Oak Meadows (A)
| Winona Park (C) |  | Montgomery Park (A+B) |  |  |  | Montgomery Park (A+B)
| Tisdall Park (C) |  |  |  | Mechanic day
7 | 8 |  | 9 |  | 10 | 11 | 12 | 13
| McCleery Park (C) |  | Shannon Park (A) |  | Eburne Park (C) | Maple Grove Park (B+C) | Shannon Park (A)
| Arbutus Park (C) |  | Tisdall Park (A) |  | Ash Park (C) | Oak Park (B) | Tisdall Park (A)
| Fraser River Park (C) |  | Winona Park (A) |  | Cambie Park (C) | Columbia Park (B+C) | Winona Park (A)
| Shannon Park (C) |  | Oak Meadows (A) |  | Marpole Park (C) |  | Oak Meadows (A)
|  |  | Montgomery Park (A+B) |  | Winona Park (C) |  | Montgomery Park (A+B)
Tisdall Park (C)
Mechanic day
14 | 15 |  | 16 |  | 17 | 18 | 19 | 20
| McCleery Park (C) |  | Shannon Park (A) |  | Buffer day | Maple Grove Park (B+C) | Shannon Park (A)
| Arbutus Park (C) |  | Tisdall Park (A) |  |  | Oak Park (B) | Tisdall Park (A)
| Fraser River Park (C) |  | Winona Park (A) |  |  | Columbia Park (B+C) | Winona Park (A)
| Shannon Park (C) |  | Oak Meadows (A) |  |  |  | Oak Meadows (A)
|  |  | Montgomery Park (A+B) |  |  |  | Montgomery Park (A+B)
Mechanic day
21 | 22 |  | 23 |  | 24 | 25 | 26 | 27
| Victoria Day |  | Shannon Park (A) |  | Eburne Park (C) | Maple Grove Park (B+C) | Shannon Park (A)
|  |  | Tisdall Park (A) |  | Ash Park (C) | Oak Park (B) | Tisdall Park (A)
|  |  | Winona Park (A) |  | Cambie Park (C) | Columbia Park (B+C) | Winona Park (A)
|  |  | Oak Meadows (A) |  | Marpole Park (C) |  | Oak Meadows (A)
|  |  | Montgomery Park (A+B) |  | Winona Park (C) |  | Montgomery Park (A+B)
Tisdall Park (C)
Mechanic day
28 | 29 |  | 30 |  | 31
| McCleery Park (C) |  | Shannon Park (A) |  | Buffer day
| Arbutus Park (C) |  | Tisdall Park (A)
| Fraser River Park (C) |  | Winona Park (A)
| Shannon Park (C) |  | Oak Meadows (A)
Montgomery Park (A+B)

## May - Central run
| Area: | SOUTH |  | Crew Lead: | Lorri Lawson | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
MAY 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
| 1 |  | 2 |  | 3 | 4 | 5 | 6
| Riley Park (C) |  | Hillcrest (A) |  | Buffer day | Gordon Park (B) | Hillcrest (A)
| Hillcrest Park (C) |  | Memorial South Park (A) |  |  | Riley Park (B) | Memorial South Park (A)
| Cartier Park (C) |  | Moberly Park (A) |  |  | George Park (B) | Moberly Park (A)
| Grays Park (C) |  |  |  |  | Ross Park (B)
Macdonald Park (C)
| Sunset Park (C) |  |  |  | Mechanic day
Tecumseh Park (C)
7 | 8 |  | 9 |  | 10 | 11 | 12 | 13
| Memorial South Park (C) |  | Hillcrest (A) |  | Riley Park (C) | Gordon Park (B) | Hillcrest (A)
| Gordon Park (C) |  | Memorial South Park (A) |  | Hillcrest Park (C) | Riley Park (B) | Memorial South Park (A)
| Ross Park (C) |  | Moberly Park (A) |  | Cartier Park (C) | George Park (B) | Moberly Park (A)
| Moberly Park (C) |  |  |  | Grays Park (C) | Ross Park (B)
| Fraserview Park (C) |  |  |  | Macdonald Park (C)
Sunset Park (C)
Tecumseh Park (C)
Mechanic day
14 | 15 |  | 16 |  | 17 | 18 | 19 | 20
| Memorial South Park (C) |  | Hillcrest (A) |  | Buffer day | Gordon Park (B) | Hillcrest (A)
| Gordon Park (C) |  | Memorial South Park (A) |  |  | Riley Park (B) | Memorial South Park (A)
| Ross Park (C) |  | Moberly Park (A) |  |  | George Park (B) | Moberly Park (A)
| Moberly Park (C) |  |  |  |  | Ross Park (B)
Fraserview Park (C)
Mechanic day
21 | 22 |  | 23 |  | 24 | 25 | 26 | 27
| Victoria Day |  | Hillcrest (A) |  | Riley Park (C) | Gordon Park (B) | Hillcrest (A)
|  |  | Memorial South Park (A) |  | Hillcrest Park (C) | Riley Park (B) | Memorial South Park (A)
|  |  | Moberly Park (A) |  | Cartier Park (C) | George Park (B) | Moberly Park (A)
[5 empty] | Grays Park (C) | Ross Park (B)
Macdonald Park (C)
Sunset Park (C)
Tecumseh Park (C)
Mechanic day
28 | 29 |  | 30 |  | 31
| Memorial South Park (C) |  | Hillcrest (A) |  | Buffer day
| Gordon Park (C) |  | Memorial South Park (A)
| Ross Park (C) |  | Moberly Park (A)
Fraserview Park (C)
Mechanic day

## May - East run
| Area: | SOUTH |  | Crew Lead: | Tony Brown | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
MAY 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
| 1 |  | 2 |  | 3 | 4 | 5 | 6
| Sparwood Park (C) |  | Bobolink Park (A) |  | Buffer day | Jones Park (B) | Bobolink Park (A)
| Captain Cook Park (C) |  | Champlain Park (A) |  |  | Earles Park (B) | Champlain Park (A)
| Rosemont Park (C) |  | Killarney Park (A) |  |  | Norquay Park (B+C) | Killarney Park (A)
| Humm Park (C) |  | Kingcrest Park (A) |  |  | Nanaimo Park (B+C) | Kingcrest Park (A)
| Riverfront Park (C) |  | Kensington Park (A) |  |  |  | Kensington Park (A)
| Champlain Park (C) |  |  |  | Mechanic day
Killarney Park (C)
7 | 8 |  | 9 |  | 10 | 11 | 12 | 13
| Kingcrest Park (C) |  | Bobolink Park (A) |  | Sparwood Park (C) | Jones Park (B) | Bobolink Park (A)
| Kensington Park (C) |  | Champlain Park (A) |  | Captain Cook Park (C) | Earles Park (B) | Champlain Park (A)
| Jones Park (C) |  | Killarney Park (A) |  | Rosemont Park (C) | Norquay Park (B+C) | Killarney Park (A)
| Earles Park (C) |  | Kingcrest Park (A) |  | Humm Park (C) | Nanaimo Park (B+C) | Kingcrest Park (A)
| Killarney Park (C) |  | Kensington Park (A) |  | Riverfront Park (C) |  | Kensington Park (A)
Champlain Park (C)
Killarney Park (C)
Mechanic day
14 | 15 |  | 16 |  | 17 | 18 | 19 | 20
| Kingcrest Park (C) |  | Bobolink Park (A) |  | Buffer day | Jones Park (B) | Bobolink Park (A)
| Kensington Park (C) |  | Champlain Park (A) |  |  | Earles Park (B) | Champlain Park (A)
| Jones Park (C) |  | Killarney Park (A) |  |  | Norquay Park (B+C) | Killarney Park (A)
| Earles Park (C) |  | Kingcrest Park (A) |  |  | Nanaimo Park (B+C) | Kingcrest Park (A)
| Killarney Park (C) |  | Kensington Park (A) |  |  |  | Kensington Park (A)
Mechanic day
21 | 22 |  | 23 |  | 24 | 25 | 26 | 27
| Victoria Day |  | Bobolink Park (A) |  | Sparwood Park (C) | Jones Park (B) | Bobolink Park (A)
|  |  | Champlain Park (A) |  | Captain Cook Park (C) | Earles Park (B) | Champlain Park (A)
|  |  | Killarney Park (A) |  | Rosemont Park (C) | Norquay Park (B+C) | Killarney Park (A)
|  |  | Kingcrest Park (A) |  | Humm Park (C) | Nanaimo Park (B+C) | Kingcrest Park (A)
|  |  | Kensington Park (A) |  | Riverfront Park (C) |  | Kensington Park (A)
Champlain Park (C)
Killarney Park (C)
Mechanic day
28 | 29 |  | 30 |  | 31
| Kingcrest Park (C) |  | Bobolink Park (A) |  | Buffer day
| Kensington Park (C) |  | Champlain Park (A)
| Jones Park (C) |  | Killarney Park (A)
| Killarney Park (C) |  | Kensington Park (A)
Mechanic day

## May - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
MAY 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
| 1 | 2 |  | 3 | 4 | 5 | 6
7 | 8 | 9 |  | 10 | 11 | 12 | 13
14 | 15 | 16 |  | 17 | 18 | 19 | 20
21 | 22 | 23 |  | 24 | 25 | 26 | 27
Victoria Day
28 | 29 | 30 |  | 31

## Jun - West run
| Area: | SOUTH |  | Crew Lead: | Coleton Fee | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
JUNE 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[6 empty] | 1 | 2 | 3
[6 empty] | Maple Grove Park (B+C) | Shannon Park (A)
[6 empty] | Oak Park (B) | Tisdall Park (A)
[6 empty] | Columbia Park (B+C) | Winona Park (A)
Oak Meadows (A)
Montgomery Park (A+B)
4 | 5 |  | 6 |  | 7 | 8 | 9 | 10
| Eburne Park (C) |  | Shannon Park (A) |  | McCleery Park (C) | Maple Grove Park (B+C) | Shannon Park (A)
| Ash Park (C) |  | Tisdall Park (A) |  | Arbutus Park (C) | Oak Park (B) | Tisdall Park (A)
| Cambie Park (C) |  | Winona Park (A) |  | Fraser River Park (C) | Columbia Park (B+C) | Winona Park (A)
| Marpole Park (C) |  | Oak Meadows (A) |  | Shannon Park (C) |  | Oak Meadows (A)
| Winona Park (C) |  | Montgomery Park (A+B) |  | Mechanic day |  | Montgomery Park (A+B)
Tisdall Park (C)
11 | 12 |  | 13 |  | 14 | 15 | 16 | 17
| Eburne Park (C) |  | Shannon Park (A) |  | Buffer day | Maple Grove Park (B+C) | Shannon Park (A)
| Ash Park (C) |  | Tisdall Park (A) |  |  | Oak Park (B) | Tisdall Park (A)
| Cambie Park (C) |  | Winona Park (A) |  |  | Columbia Park (B+C) | Winona Park (A)
| Marpole Park (C) |  | Oak Meadows (A) |  |  |  | Oak Meadows (A)
| Winona Park (C) |  | Montgomery Park (A+B) |  |  |  | Montgomery Park (A+B)
| Tisdall Park (C) |  |  |  | Mechanic day
18 | 19 |  | 20 |  | 21 | 22 | 23 | 24
| McCleery Park (C) |  | Shannon Park (A) |  | Eburne Park (C) | Maple Grove Park (B+C) | Shannon Park (A)
| Arbutus Park (C) |  | Tisdall Park (A) |  | Ash Park (C) | Oak Park (B) | Tisdall Park (A)
| Fraser River Park (C) |  | Winona Park (A) |  | Cambie Park (C) | Columbia Park (B+C) | Winona Park (A)
| Shannon Park (C) |  | Oak Meadows (A) |  | Marpole Park (C) |  | Oak Meadows (A)
|  |  | Montgomery Park (A+B) |  | Winona Park (C) |  | Montgomery Park (A+B)
Tisdall Park (C)
Mechanic day
25 | 26 |  | 27 |  | 28 | 29 | 30
| McCleery Park (C) |  | Shannon Park (A) |  | Buffer day | Maple Grove Park (B+C) | Shannon Park (A)
| Arbutus Park (C) |  | Tisdall Park (A) |  |  | Oak Park (B) | Tisdall Park (A)
| Fraser River Park (C) |  | Winona Park (A) |  |  | Columbia Park (B+C) | Winona Park (A)
| Shannon Park (C) |  | Oak Meadows (A) |  |  |  | Oak Meadows (A)
|  |  | Montgomery Park (A+B) |  |  |  | Montgomery Park (A+B)

## Jun - Central run
| Area: | SOUTH |  | Crew Lead: | Lorri Lawson | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
JUNE 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[6 empty] | 1 | 2 | 3
[6 empty] | Gordon Park (B) | Hillcrest (A)
[6 empty] | Riley Park (B) | Memorial South Park (A)
[6 empty] | George Park (B) | Moberly Park (A)
Ross Park (B)
4 | 5 |  | 6 |  | 7 | 8 | 9 | 10
| Riley Park (C) |  | Hillcrest (A) |  | Memorial South Park (C) | Gordon Park (B) | Hillcrest (A)
| Hillcrest Park (C) |  | Memorial South Park (A) |  | Gordon Park (C) | Riley Park (B) | Memorial South Park (A)
| Cartier Park (C) |  | Moberly Park (A) |  | Ross Park (C) | George Park (B) | Moberly Park (A)
| Grays Park (C) |  |  |  | Moberly Park (C) | Ross Park (B)
| Macdonald Park (C) |  |  |  | Fraserview Park (C)
| Sunset Park (C) |  |  |  | Mechanic day
Tecumseh Park (C)
11 | 12 |  | 13 |  | 14 | 15 | 16 | 17
| Riley Park (C) |  | Hillcrest (A) |  | Buffer day | Gordon Park (B) | Hillcrest (A)
| Hillcrest Park (C) |  | Memorial South Park (A) |  |  | Riley Park (B) | Memorial South Park (A)
| Cartier Park (C) |  | Moberly Park (A) |  |  | George Park (B) | Moberly Park (A)
| Grays Park (C) |  |  |  |  | Ross Park (B)
Macdonald Park (C)
| Sunset Park (C) |  |  |  | Mechanic day
Tecumseh Park (C)
18 | 19 |  | 20 |  | 21 | 22 | 23 | 24
| Memorial South Park (C) |  | Hillcrest (A) |  | Riley Park (C) | Gordon Park (B) | Hillcrest (A)
| Gordon Park (C) |  | Memorial South Park (A) |  | Hillcrest Park (C) | Riley Park (B) | Memorial South Park (A)
| Ross Park (C) |  | Moberly Park (A) |  | Cartier Park (C) | George Park (B) | Moberly Park (A)
| Moberly Park (C) |  |  |  | Grays Park (C) | Ross Park (B)
| Fraserview Park (C) |  |  |  | Macdonald Park (C)
Sunset Park (C)
Tecumseh Park (C)
Mechanic day
25 | 26 |  | 27 |  | 28 | 29 | 30
| Memorial South Park (C) |  | Hillcrest (A) |  | Buffer day | Gordon Park (B) | Hillcrest (A)
| Gordon Park (C) |  | Memorial South Park (A) |  |  | Riley Park (B) | Memorial South Park (A)
| Ross Park (C) |  | Moberly Park (A) |  |  | George Park (B) | Moberly Park (A)
| Moberly Park (C) |  |  |  |  | Ross Park (B)
Mechanic day

## Jun - East run
| Area: | SOUTH |  | Crew Lead: | Tony Brown | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
JUNE 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[6 empty] | 1 | 2 | 3
[6 empty] | Jones Park (B) | Bobolink Park (A)
[6 empty] | Earles Park (B) | Champlain Park (A)
[6 empty] | Norquay Park (B+C) | Killarney Park (A)
[6 empty] | Nanaimo Park (B+C) | Kingcrest Park (A)
Kensington Park (A)
4 | 5 |  | 6 |  | 7 | 8 | 9 | 10
| Sparwood Park (C) |  | Bobolink Park (A) |  | Kingcrest Park (C) | Jones Park (B) | Bobolink Park (A)
| Captain Cook Park (C) |  | Champlain Park (A) |  | Kensington Park (C) | Earles Park (B) | Champlain Park (A)
| Rosemont Park (C) |  | Killarney Park (A) |  | Jones Park (C) | Norquay Park (B+C) | Killarney Park (A)
| Humm Park (C) |  | Kingcrest Park (A) |  | Earles Park (C) | Nanaimo Park (B+C) | Kingcrest Park (A)
| Riverfront Park (C) |  | Kensington Park (A) |  | Killarney Park (C) |  | Kensington Park (A)
| Champlain Park (C) |  |  |  | Mechanic day
Killarney Park (C)
11 | 12 |  | 13 |  | 14 | 15 | 16 | 17
| Sparwood Park (C) |  | Bobolink Park (A) |  | Buffer day | Jones Park (B) | Bobolink Park (A)
| Captain Cook Park (C) |  | Champlain Park (A) |  |  | Earles Park (B) | Champlain Park (A)
| Rosemont Park (C) |  | Killarney Park (A) |  |  | Norquay Park (B+C) | Killarney Park (A)
| Humm Park (C) |  | Kingcrest Park (A) |  |  | Nanaimo Park (B+C) | Kingcrest Park (A)
| Riverfront Park (C) |  | Kensington Park (A) |  |  |  | Kensington Park (A)
| Champlain Park (C) |  |  |  | Mechanic day
Killarney Park (C)
18 | 19 |  | 20 |  | 21 | 22 | 23 | 24
| Kingcrest Park (C) |  | Bobolink Park (A) |  | Sparwood Park (C) | Jones Park (B) | Bobolink Park (A)
| Kensington Park (C) |  | Champlain Park (A) |  | Captain Cook Park (C) | Earles Park (B) | Champlain Park (A)
| Jones Park (C) |  | Killarney Park (A) |  | Rosemont Park (C) | Norquay Park (B+C) | Killarney Park (A)
| Earles Park (C) |  | Kingcrest Park (A) |  | Humm Park (C) | Nanaimo Park (B+C) | Kingcrest Park (A)
| Killarney Park (C) |  | Kensington Park (A) |  | Riverfront Park (C) |  | Kensington Park (A)
Champlain Park (C)
Killarney Park (C)
Mechanic day
25 | 26 |  | 27 |  | 28 | 29 | 30
| Kingcrest Park (C) |  | Bobolink Park (A) |  | Buffer day | Jones Park (B) | Bobolink Park (A)
| Kensington Park (C) |  | Champlain Park (A) |  |  | Earles Park (B) | Champlain Park (A)
| Jones Park (C) |  | Killarney Park (A) |  |  | Norquay Park (B+C) | Killarney Park (A)
| Earles Park (C) |  | Kingcrest Park (A) |  |  | Nanaimo Park (B+C) | Kingcrest Park (A)
Mechanic day

## Jun - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
JUNE 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
[5 empty] | 1 | 2 | 3
4 | 5 | 6 |  | 7 | 8 | 9 | 10
11 | 12 | 13 |  | 14 | 15 | 16 | 17
18 | 19 | 20 |  | 21 | 22 | 23 | 24
25 | 26 | 27 |  | 28 | 29 | 30

## Jul - West run
| Area: | SOUTH |  | Crew Lead: | Coleton Fee | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
JULY 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
2 | 3 |  | 4 |  | 5 | 6 | 7 | 8
| Canada Day Stat |  | Shannon Park (A) |  | Eburne Park (C) | Maple Grove Park (B+C) | Shannon Park (A)
|  |  | Tisdall Park (A) |  | Ash Park (C) | Oak Park (B) | Tisdall Park (A)
|  |  | Winona Park (A) |  | Cambie Park (C) | Columbia Park (B+C) | Winona Park (A)
|  |  | Oak Meadows (A) |  | Marpole Park (C) |  | Oak Meadows (A)
|  |  | Montgomery Park (A+B) |  | Winona Park (C) |  | Montgomery Park (A+B)
Tisdall Park (C)
Mechanic day
9 | 10 |  | 11 |  | 12 | 13 | 14 | 15
| McCleery Park (C) |  | Shannon Park (A) |  | Buffer day | Maple Grove Park (B+C) | Shannon Park (A)
| Arbutus Park (C) |  | Tisdall Park (A) |  |  | Oak Park (B) | Tisdall Park (A)
| Fraser River Park (C) |  | Winona Park (A) |  |  | Columbia Park (B+C) | Winona Park (A)
| Shannon Park (C) |  | Oak Meadows (A) |  |  |  | Oak Meadows (A)
|  |  | Montgomery Park (A+B) |  |  |  | Montgomery Park (A+B)
Mechanic day
16 | 17 |  | 18 |  | 19 | 20 | 21 | 22
| Eburne Park (C) |  | Shannon Park (A) |  | McCleery Park (C) | Maple Grove Park (B+C) | Shannon Park (A)
| Ash Park (C) |  | Tisdall Park (A) |  | Arbutus Park (C) | Oak Park (B) | Tisdall Park (A)
| Cambie Park (C) |  | Winona Park (A) |  | Fraser River Park (C) | Columbia Park (B+C) | Winona Park (A)
| Marpole Park (C) |  | Oak Meadows (A) |  | Shannon Park (C) |  | Oak Meadows (A)
| Winona Park (C) |  | Montgomery Park (A+B) |  | Mechanic day |  | Montgomery Park (A+B)
Tisdall Park (C)
23 | 24 |  | 25 |  | 26 | 27 | 28 | 29
| Eburne Park (C) |  | Shannon Park (A) |  | Buffer day | Maple Grove Park (B+C) | Shannon Park (A)
| Ash Park (C) |  | Tisdall Park (A) |  |  | Oak Park (B) | Tisdall Park (A)
| Cambie Park (C) |  | Winona Park (A) |  |  | Columbia Park (B+C) | Winona Park (A)
| Marpole Park (C) |  | Oak Meadows (A) |  |  |  | Oak Meadows (A)
| Winona Park (C) |  | Montgomery Park (A+B) |  |  |  | Montgomery Park (A+B)
| Tisdall Park (C) |  |  |  | Mechanic day
30 | 31
McCleery Park (C)
Arbutus Park (C)
Fraser River Park (C)
Shannon Park (C)

## Jul - Central run
| Area: | SOUTH |  | Crew Lead: | Lorri Lawson | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
JULY 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
2 | 3 |  | 4 |  | 5 | 6 | 7 | 8
| Canada Day Stat |  | Hillcrest (A) |  | Riley Park (C) | Gordon Park (B) | Hillcrest (A)
|  |  | Memorial South Park (A) |  | Hillcrest Park (C) | Riley Park (B) | Memorial South Park (A)
|  |  | Moberly Park (A) |  | Cartier Park (C) | George Park (B) | Moberly Park (A)
[5 empty] | Grays Park (C) | Ross Park (B)
Macdonald Park (C)
Sunset Park (C)
Tecumseh Park (C)
Mechanic day
9 | 10 |  | 11 |  | 12 | 13 | 14 | 15
| Memorial South Park (C) |  | Hillcrest (A) |  | Buffer day | Gordon Park (B) | Hillcrest (A)
| Gordon Park (C) |  | Memorial South Park (A) |  |  | Riley Park (B) | Memorial South Park (A)
| Ross Park (C) |  | Moberly Park (A) |  |  | George Park (B) | Moberly Park (A)
| Moberly Park (C) |  |  |  |  | Ross Park (B)
Fraserview Park (C)
Mechanic day
16 | 17 |  | 18 |  | 19 | 20 | 21 | 22
| Riley Park (C) |  | Hillcrest (A) |  | Memorial South Park (C) | Gordon Park (B) | Hillcrest (A)
| Hillcrest Park (C) |  | Memorial South Park (A) |  | Gordon Park (C) | Riley Park (B) | Memorial South Park (A)
| Cartier Park (C) |  | Moberly Park (A) |  | Ross Park (C) | George Park (B) | Moberly Park (A)
| Grays Park (C) |  |  |  | Moberly Park (C) | Ross Park (B)
| Macdonald Park (C) |  |  |  | Fraserview Park (C)
| Sunset Park (C) |  |  |  | Mechanic day
Tecumseh Park (C)
23 | 24 |  | 25 |  | 26 | 27 | 28 | 29
| Riley Park (C) |  | Hillcrest (A) |  | Buffer day | Gordon Park (B) | Hillcrest (A)
| Hillcrest Park (C) |  | Memorial South Park (A) |  |  | Riley Park (B) | Memorial South Park (A)
| Cartier Park (C) |  | Moberly Park (A) |  |  | George Park (B) | Moberly Park (A)
| Grays Park (C) |  |  |  |  | Ross Park (B)
Macdonald Park (C)
| Sunset Park (C) |  |  |  | Mechanic day
Tecumseh Park (C)
30 | 31
Memorial South Park (C)
Gordon Park (C)
Ross Park (C)
Moberly Park (C)

## Jul - East run
| Area: | SOUTH |  | Crew Lead: | Tony Brown | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
JULY 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
2 | 3 |  | 4 |  | 5 | 6 | 7 | 8
| Canada Day Stat |  | Bobolink Park (A) |  | Sparwood Park (C) | Jones Park (B) | Bobolink Park (A)
|  |  | Champlain Park (A) |  | Captain Cook Park (C) | Earles Park (B) | Champlain Park (A)
|  |  | Killarney Park (A) |  | Rosemont Park (C) | Norquay Park (B+C) | Killarney Park (A)
|  |  | Kingcrest Park (A) |  | Humm Park (C) | Nanaimo Park (B+C) | Kingcrest Park (A)
|  |  | Kensington Park (A) |  | Riverfront Park (C) |  | Kensington Park (A)
Champlain Park (C)
Killarney Park (C)
Mechanic day
9 | 10 |  | 11 |  | 12 | 13 | 14 | 15
| Kingcrest Park (C) |  | Bobolink Park (A) |  | Buffer day | Jones Park (B) | Bobolink Park (A)
| Kensington Park (C) |  | Champlain Park (A) |  |  | Earles Park (B) | Champlain Park (A)
| Jones Park (C) |  | Killarney Park (A) |  |  | Norquay Park (B+C) | Killarney Park (A)
| Earles Park (C) |  | Kingcrest Park (A) |  |  | Nanaimo Park (B+C) | Kingcrest Park (A)
| Killarney Park (C) |  | Kensington Park (A) |  |  |  | Kensington Park (A)
Mechanic day
16 | 17 |  | 18 |  | 19 | 20 | 21 | 22
| Sparwood Park (C) |  | Bobolink Park (A) |  | Kingcrest Park (C) | Jones Park (B) | Bobolink Park (A)
| Captain Cook Park (C) |  | Champlain Park (A) |  | Kensington Park (C) | Earles Park (B) | Champlain Park (A)
| Rosemont Park (C) |  | Killarney Park (A) |  | Jones Park (C) | Norquay Park (B+C) | Killarney Park (A)
| Humm Park (C) |  | Kingcrest Park (A) |  | Earles Park (C) | Nanaimo Park (B+C) | Kingcrest Park (A)
| Riverfront Park (C) |  | Kensington Park (A) |  | Killarney Park (C) |  | Kensington Park (A)
| Champlain Park (C) |  |  |  | Mechanic day
Killarney Park (C)
23 | 24 |  | 25 |  | 26 | 27 | 28 | 29
| Sparwood Park (C) |  | Bobolink Park (A) |  | Buffer day | Jones Park (B) | Bobolink Park (A)
| Captain Cook Park (C) |  | Champlain Park (A) |  |  | Earles Park (B) | Champlain Park (A)
| Rosemont Park (C) |  | Killarney Park (A) |  |  | Norquay Park (B+C) | Killarney Park (A)
| Humm Park (C) |  | Kingcrest Park (A) |  |  | Nanaimo Park (B+C) | Kingcrest Park (A)
| Riverfront Park (C) |  | Kensington Park (A) |  |  |  | Kensington Park (A)
| Champlain Park (C) |  |  |  | Mechanic day
Killarney Park (C)
30 | 31
Kingcrest Park (C)
Kensington Park (C)
Jones Park (C)
Earles Park (C)

## Jul - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
JULY 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
2 | 3 | 4 |  | 5 | 6 | 7 | 8
Canada Day Stat
9 | 10 | 11 |  | 12 | 13 | 14 | 15
16 | 17 | 18 |  | 19 | 20 | 21 | 22
23 | 24 | 25 |  | 26 | 27 | 28 | 29
30 | 31

## Aug - West run
| Area: | SOUTH |  | Crew Lead: | Coleton Fee | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
AUGUST 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
|  |  | 1 |  | 2 | 3 | 4 | 5
|  |  | Shannon Park (A) |  | Eburne Park (C) | Maple Grove Park (B+C) | Shannon Park (A)
|  |  | Tisdall Park (A) |  | Ash Park (C) | Oak Park (B) | Tisdall Park (A)
|  |  | Winona Park (A) |  | Cambie Park (C) | Columbia Park (B+C) | Winona Park (A)
|  |  | Oak Meadows (A) |  | Marpole Park (C) |  | Oak Meadows (A)
|  |  | Montgomery Park (A+B) |  | Winona Park (C) |  | Montgomery Park (A+B)
Tisdall Park (C)
Mechanic day
6 | 7 |  | 8 |  | 9 | 10 | 11 | 12
| BC Day |  | Shannon Park (A) |  | Buffer day | Maple Grove Park (B+C) | Shannon Park (A)
|  |  | Tisdall Park (A) |  |  | Oak Park (B) | Tisdall Park (A)
|  |  | Winona Park (A) |  |  | Columbia Park (B+C) | Winona Park (A)
|  |  | Oak Meadows (A) |  |  |  | Oak Meadows (A)
|  |  | Montgomery Park (A+B) |  |  |  | Montgomery Park (A+B)
Mechanic day
13 | 14 |  | 15 |  | 16 | 17 | 18 | 19
| McCleery Park (C) |  | Shannon Park (A) |  | Eburne Park (C) | Maple Grove Park (B+C) | Shannon Park (A)
| Arbutus Park (C) |  | Tisdall Park (A) |  | Ash Park (C) | Oak Park (B) | Tisdall Park (A)
| Fraser River Park (C) |  | Winona Park (A) |  | Cambie Park (C) | Columbia Park (B+C) | Winona Park (A)
| Shannon Park (C) |  | Oak Meadows (A) |  | Marpole Park (C) |  | Oak Meadows (A)
|  |  | Montgomery Park (A+B) |  | Winona Park (C) |  | Montgomery Park (A+B)
Tisdall Park (C)
Mechanic day
20 | 21 |  | 22 |  | 23 | 24 | 25 | 26
| McCleery Park (C) |  | Shannon Park (A) |  | Buffer day | Maple Grove Park (B+C) | Shannon Park (A)
| Arbutus Park (C) |  | Tisdall Park (A) |  |  | Oak Park (B) | Tisdall Park (A)
| Fraser River Park (C) |  | Winona Park (A) |  |  | Columbia Park (B+C) | Winona Park (A)
| Shannon Park (C) |  | Oak Meadows (A) |  |  |  | Oak Meadows (A)
|  |  | Montgomery Park (A+B) |  |  |  | Montgomery Park (A+B)
Mechanic day
27 | 28 |  | 29 |  | 30 | 31
| Eburne Park (C) |  | Shannon Park (A) |  | McCleery Park (C) | Maple Grove Park (B+C)
| Ash Park (C) |  | Tisdall Park (A) |  | Arbutus Park (C) | Oak Park (B)
| Cambie Park (C) |  | Winona Park (A) |  | Fraser River Park (C) | Columbia Park (B+C)
| Marpole Park (C) |  | Oak Meadows (A) |  | Shannon Park (C)
| Winona Park (C) |  | Montgomery Park (A+B) |  | Mechanic day

## Aug - Central run
| Area: | SOUTH |  | Crew Lead: | Lorri Lawson | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
AUGUST 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
|  |  | 1 |  | 2 | 3 | 4 | 5
|  |  | Hillcrest (A) |  | Riley Park (C) | Gordon Park (B) | Hillcrest (A)
|  |  | Memorial South Park (A) |  | Hillcrest Park (C) | Riley Park (B) | Memorial South Park (A)
|  |  | Moberly Park (A) |  | Cartier Park (C) | George Park (B) | Moberly Park (A)
[5 empty] | Grays Park (C) | Ross Park (B)
Macdonald Park (C)
Sunset Park (C)
Tecumseh Park (C)
Mechanic day
6 | 7 |  | 8 |  | 9 | 10 | 11 | 12
| BC Day |  | Hillcrest (A) |  | Buffer day | Gordon Park (B) | Hillcrest (A)
|  |  | Memorial South Park (A) |  |  | Riley Park (B) | Memorial South Park (A)
|  |  | Moberly Park (A) |  |  | George Park (B) | Moberly Park (A)
Ross Park (B)
Mechanic day
13 | 14 |  | 15 |  | 16 | 17 | 18 | 19
| Memorial South Park (C) |  | Hillcrest (A) |  | Riley Park (C) | Gordon Park (B) | Hillcrest (A)
| Gordon Park (C) |  | Memorial South Park (A) |  | Hillcrest Park (C) | Riley Park (B) | Memorial South Park (A)
| Ross Park (C) |  | Moberly Park (A) |  | Cartier Park (C) | George Park (B) | Moberly Park (A)
| Moberly Park (C) |  |  |  | Grays Park (C) | Ross Park (B)
| Fraserview Park (C) |  |  |  | Macdonald Park (C)
Sunset Park (C)
Tecumseh Park (C)
Mechanic day
20 | 21 |  | 22 |  | 23 | 24 | 25 | 26
| Memorial South Park (C) |  | Hillcrest (A) |  | Buffer day | Gordon Park (B) | Hillcrest (A)
| Gordon Park (C) |  | Memorial South Park (A) |  |  | Riley Park (B) | Memorial South Park (A)
| Ross Park (C) |  | Moberly Park (A) |  |  | George Park (B) | Moberly Park (A)
| Moberly Park (C) |  |  |  |  | Ross Park (B)
Fraserview Park (C)
Mechanic day
27 | 28 |  | 29 |  | 30 | 31
| Riley Park (C) |  | Hillcrest (A) |  | Memorial South Park (C) | Gordon Park (B)
| Hillcrest Park (C) |  | Memorial South Park (A) |  | Gordon Park (C) | Riley Park (B)
| Cartier Park (C) |  | Moberly Park (A) |  | Ross Park (C) | George Park (B)
| Macdonald Park (C) |  |  |  | Fraserview Park (C)
| Sunset Park (C) |  |  |  | Mechanic day
Tecumseh Park (C)

## Aug - East run
| Area: | SOUTH |  | Crew Lead: | Tony Brown | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
AUGUST 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
|  |  | 1 |  | 2 | 3 | 4 | 5
|  |  | Bobolink Park (A) |  | Sparwood Park (C) | Jones Park (B) | Bobolink Park (A)
|  |  | Champlain Park (A) |  | Captain Cook Park (C) | Earles Park (B) | Champlain Park (A)
|  |  | Killarney Park (A) |  | Rosemont Park (C) | Norquay Park (B+C) | Killarney Park (A)
|  |  | Kingcrest Park (A) |  | Humm Park (C) | Nanaimo Park (B+C) | Kingcrest Park (A)
|  |  | Kensington Park (A) |  | Riverfront Park (C) |  | Kensington Park (A)
Champlain Park (C)
Killarney Park (C)
Mechanic day
6 | 7 |  | 8 |  | 9 | 10 | 11 | 12
| BC Day |  | Bobolink Park (A) |  | Buffer day | Jones Park (B) | Bobolink Park (A)
|  |  | Champlain Park (A) |  |  | Earles Park (B) | Champlain Park (A)
|  |  | Killarney Park (A) |  |  | Norquay Park (B+C) | Killarney Park (A)
|  |  | Kingcrest Park (A) |  |  | Nanaimo Park (B+C) | Kingcrest Park (A)
|  |  | Kensington Park (A) |  |  |  | Kensington Park (A)
Mechanic day
13 | 14 |  | 15 |  | 16 | 17 | 18 | 19
| Kingcrest Park (C) |  | Bobolink Park (A) |  | Sparwood Park (C) | Jones Park (B) | Bobolink Park (A)
| Kensington Park (C) |  | Champlain Park (A) |  | Captain Cook Park (C) | Earles Park (B) | Champlain Park (A)
| Jones Park (C) |  | Killarney Park (A) |  | Rosemont Park (C) | Norquay Park (B+C) | Killarney Park (A)
| Earles Park (C) |  | Kingcrest Park (A) |  | Humm Park (C) | Nanaimo Park (B+C) | Kingcrest Park (A)
| Killarney Park (C) |  | Kensington Park (A) |  | Riverfront Park (C) |  | Kensington Park (A)
Champlain Park (C)
Killarney Park (C)
Mechanic day
20 | 21 |  | 22 |  | 23 | 24 | 25 | 26
| Kingcrest Park (C) |  | Bobolink Park (A) |  | Buffer day | Jones Park (B) | Bobolink Park (A)
| Kensington Park (C) |  | Champlain Park (A) |  |  | Earles Park (B) | Champlain Park (A)
| Jones Park (C) |  | Killarney Park (A) |  |  | Norquay Park (B+C) | Killarney Park (A)
| Earles Park (C) |  | Kingcrest Park (A) |  |  | Nanaimo Park (B+C) | Kingcrest Park (A)
| Killarney Park (C) |  | Kensington Park (A) |  |  |  | Kensington Park (A)
Mechanic day
27 | 28 |  | 29 |  | 30 | 31
| Sparwood Park (C) |  | Bobolink Park (A) |  | Kingcrest Park (C) | Jones Park (B)
| Captain Cook Park (C) |  | Champlain Park (A) |  | Kensington Park (C) | Earles Park (B)
| Rosemont Park (C) |  | Killarney Park (A) |  | Jones Park (C) | Norquay Park (B+C)
| Riverfront Park (C) |  | Kensington Park (A) |  | Killarney Park (C)
| Champlain Park (C) |  |  |  | Mechanic day
Killarney Park (C)

## Aug - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
AUGUST 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
|  | 1 |  | 2 | 3 | 4 | 5
6 | 7 | 8 |  | 9 | 10 | 11 | 12
BC Day
13 | 14 | 15 |  | 16 | 17 | 18 | 19
20 | 21 | 22 |  | 23 | 24 | 25 | 26
27 | 28 | 29 |  | 30 | 31

## Sept - West run
| Area: | SOUTH |  | Crew Lead: | Coleton Fee | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
SEPTEMBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[7 empty] | 1 | 2
Shannon Park (A)
Tisdall Park (A)
Winona Park (A)
Oak Meadows (A)
Montgomery Park (A+B)
3 | 4 |  | 5 |  | 6 | 7 | 8 | 9
| Labour Day |  | Shannon Park (A) |  | Buffer day | Maple Grove Park (B+C) | Shannon Park (A)
|  |  | Tisdall Park (A) |  |  | Oak Park (B) | Tisdall Park (A)
|  |  | Winona Park (A) |  |  | Columbia Park (B+C) | Winona Park (A)
|  |  | Oak Meadows (A) |  |  |  | Oak Meadows (A)
|  |  | Montgomery Park (A+B) |  |  |  | Montgomery Park (A+B)
Mechanic day
10 | 11 |  | 12 |  | 13 | 14 | 15 | 16
| Eburne Park (C) |  | Shannon Park (A) |  | McCleery Park (C) | Maple Grove Park (B+C) | Shannon Park (A)
| Ash Park (C) |  | Tisdall Park (A) |  | Arbutus Park (C) | Oak Park (B) | Tisdall Park (A)
| Cambie Park (C) |  | Winona Park (A) |  | Fraser River Park (C) | Columbia Park (B+C) | Winona Park (A)
| Marpole Park (C) |  | Oak Meadows (A) |  | Shannon Park (C) |  | Oak Meadows (A)
| Winona Park (C) |  | Montgomery Park (A+B) |  | Mechanic day |  | Montgomery Park (A+B)
Tisdall Park (C)
17 | 18 |  | 19 |  | 20 | 21 | 22 | 23
| Eburne Park (C) |  | Shannon Park (A) |  | Buffer day | Maple Grove Park (B+C) | Shannon Park (A)
| Ash Park (C) |  | Tisdall Park (A) |  |  | Oak Park (B) | Tisdall Park (A)
| Cambie Park (C) |  | Winona Park (A) |  |  | Columbia Park (B+C) | Winona Park (A)
| Marpole Park (C) |  | Oak Meadows (A) |  |  |  | Oak Meadows (A)
| Winona Park (C) |  | Montgomery Park (A+B) |  |  |  | Montgomery Park (A+B)
| Tisdall Park (C) |  |  |  | Mechanic day
24 | 25 |  | 26 |  | 27 | 28 | 29 | 30
| McCleery Park (C) |  | Shannon Park (A) |  | Eburne Park (C) | Maple Grove Park (B+C) | Shannon Park (A)
| Arbutus Park (C) |  | Tisdall Park (A) |  | Ash Park (C) | Oak Park (B) | Tisdall Park (A)
| Fraser River Park (C) |  | Winona Park (A) |  | Cambie Park (C) | Columbia Park (B+C) | Winona Park (A)
| Shannon Park (C) |  | Oak Meadows (A) |  | Marpole Park (C) |  | Oak Meadows (A)
|  |  | Montgomery Park (A+B) |  | Winona Park (C) |  | Montgomery Park (A+B)
Mechanic day

## Sept - Central run
| Area: | SOUTH |  | Crew Lead: | Lorri Lawson | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
SEPTEMBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[7 empty] | 1 | 2
Hillcrest (A)
Memorial South Park (A)
Moberly Park (A)
3 | 4 |  | 5 |  | 6 | 7 | 8 | 9
| Labour Day |  | Hillcrest (A) |  | Buffer day | Gordon Park (B) | Hillcrest (A)
|  |  | Memorial South Park (A) |  |  | Riley Park (B) | Memorial South Park (A)
|  |  | Moberly Park (A) |  |  | George Park (B) | Moberly Park (A)
Ross Park (B)
Mechanic day
10 | 11 |  | 12 |  | 13 | 14 | 15 | 16
| Riley Park (C) |  | Hillcrest (A) |  | Memorial South Park (C) | Gordon Park (B) | Hillcrest (A)
| Hillcrest Park (C) |  | Memorial South Park (A) |  | Gordon Park (C) | Riley Park (B) | Memorial South Park (A)
| Cartier Park (C) |  | Moberly Park (A) |  | Ross Park (C) | George Park (B) | Moberly Park (A)
| Grays Park (C) |  |  |  | Moberly Park (C) | Ross Park (B)
| Macdonald Park (C) |  |  |  | Fraserview Park (C)
| Sunset Park (C) |  |  |  | Mechanic day
Tecumseh Park (C)
17 | 18 |  | 19 |  | 20 | 21 | 22 | 23
| Riley Park (C) |  | Hillcrest (A) |  | Buffer day | Gordon Park (B) | Hillcrest (A)
| Hillcrest Park (C) |  | Memorial South Park (A) |  |  | Riley Park (B) | Memorial South Park (A)
| Cartier Park (C) |  | Moberly Park (A) |  |  | George Park (B) | Moberly Park (A)
| Grays Park (C) |  |  |  |  | Ross Park (B)
Macdonald Park (C)
| Sunset Park (C) |  |  |  | Mechanic day
Tecumseh Park (C)
24 | 25 |  | 26 |  | 27 | 28 | 29 | 30
| Memorial South Park (C) |  | Hillcrest (A) |  | Riley Park (C) | Gordon Park (B) | Hillcrest (A)
| Gordon Park (C) |  | Memorial South Park (A) |  | Hillcrest Park (C) | Riley Park (B) | Memorial South Park (A)
| Ross Park (C) |  | Moberly Park (A) |  | Cartier Park (C) | George Park (B) | Moberly Park (A)
| Moberly Park (C) |  |  |  | Grays Park (C) | Ross Park (B)
| Fraserview Park (C) |  |  |  | Macdonald Park (C)
Tecumseh Park (C)
Mechanic day

## Sept - East run
| Area: | SOUTH |  | Crew Lead: | Tony Brown | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
SEPTEMBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[7 empty] | 1 | 2
Bobolink Park (A)
Champlain Park (A)
Killarney Park (A)
Kingcrest Park (A)
Kensington Park (A)
3 | 4 |  | 5 |  | 6 | 7 | 8 | 9
| Labour Day |  | Bobolink Park (A) |  | Buffer day | Jones Park (B) | Bobolink Park (A)
|  |  | Champlain Park (A) |  |  | Earles Park (B) | Champlain Park (A)
|  |  | Killarney Park (A) |  |  | Norquay Park (B+C) | Killarney Park (A)
|  |  | Kingcrest Park (A) |  |  | Nanaimo Park (B+C) | Kingcrest Park (A)
|  |  | Kensington Park (A) |  |  |  | Kensington Park (A)
Mechanic day
10 | 11 |  | 12 |  | 13 | 14 | 15 | 16
| Sparwood Park (C) |  | Bobolink Park (A) |  | Kingcrest Park (C) | Jones Park (B) | Bobolink Park (A)
| Captain Cook Park (C) |  | Champlain Park (A) |  | Kensington Park (C) | Earles Park (B) | Champlain Park (A)
| Rosemont Park (C) |  | Killarney Park (A) |  | Jones Park (C) | Norquay Park (B+C) | Killarney Park (A)
| Humm Park (C) |  | Kingcrest Park (A) |  | Earles Park (C) | Nanaimo Park (B+C) | Kingcrest Park (A)
| Riverfront Park (C) |  | Kensington Park (A) |  | Killarney Park (C) |  | Kensington Park (A)
| Champlain Park (C) |  |  |  | Mechanic day
Killarney Park (C)
17 | 18 |  | 19 |  | 20 | 21 | 22 | 23
| Sparwood Park (C) |  | Bobolink Park (A) |  | Buffer day | Jones Park (B) | Bobolink Park (A)
| Captain Cook Park (C) |  | Champlain Park (A) |  |  | Earles Park (B) | Champlain Park (A)
| Rosemont Park (C) |  | Killarney Park (A) |  |  | Norquay Park (B+C) | Killarney Park (A)
| Humm Park (C) |  | Kingcrest Park (A) |  |  | Nanaimo Park (B+C) | Kingcrest Park (A)
| Riverfront Park (C) |  | Kensington Park (A) |  |  |  | Kensington Park (A)
| Champlain Park (C) |  |  |  | Mechanic day
Killarney Park (C)
24 | 25 |  | 26 |  | 27 | 28 | 29 | 30
| Kingcrest Park (C) |  | Bobolink Park (A) |  | Sparwood Park (C) | Jones Park (B) | Bobolink Park (A)
| Kensington Park (C) |  | Champlain Park (A) |  | Captain Cook Park (C) | Earles Park (B) | Champlain Park (A)
| Jones Park (C) |  | Killarney Park (A) |  | Rosemont Park (C) | Norquay Park (B+C) | Killarney Park (A)
| Earles Park (C) |  | Kingcrest Park (A) |  | Humm Park (C) | Nanaimo Park (B+C) | Kingcrest Park (A)
| Killarney Park (C) |  | Kensington Park (A) |  | Riverfront Park (C) |  | Kensington Park (A)
Killarney Park (C)
Mechanic day

## Sept - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
SEPTEMBER 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
[6 empty] | 1 | 2
3 | 4 | 5 |  | 6 | 7 | 8 | 9
Labour Day
10 | 11 | 12 |  | 13 | 14 | 15 | 16
17 | 18 | 19 |  | 20 | 21 | 22 | 23
24 | 25 | 26 |  | 27 | 28 | 29 | 30

## Oct - West run
| Area: | SOUTH |  | Crew Lead: | Coleton Fee | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
OCTOBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
1 | 2 |  | 3 |  | 4 | 5 | 6 | 7
| McCleery Park (C) |  | Shannon Park (A) |  | Buffer day | Maple Grove Park (B+C) | Shannon Park (A)
| Arbutus Park (C) |  | Tisdall Park (A) |  |  | Oak Park (B) | Tisdall Park (A)
| Fraser River Park (C) |  | Winona Park (A) |  |  | Columbia Park (B+C) | Winona Park (A)
| Shannon Park (C) |  | Oak Meadows (A) |  |  |  | Oak Meadows (A)
|  |  | Montgomery Park (A+B) |  |  |  | Montgomery Park (A+B)
Mechanic day
8 | 9 |  | 10 |  | 11 | 12 | 13 | 14
| Thanksgiving Day |  | Shannon Park (A) |  | Eburne Park (C) | Maple Grove Park (B+C) | Shannon Park (A)
|  |  | Tisdall Park (A) |  | Ash Park (C) | Oak Park (B) | Tisdall Park (A)
|  |  | Winona Park (A) |  | Cambie Park (C) | Columbia Park (B+C) | Winona Park (A)
|  |  | Oak Meadows (A) |  | Marpole Park (C) |  | Oak Meadows (A)
|  |  | Montgomery Park (A+B) |  | Winona Park (C) |  | Montgomery Park (A+B)
Tisdall Park (C)
Mechanic day
15 | 16 |  | 17 |  | 18 | 19 | 20 | 21
| McCleery Park (C) |  | Shannon Park (A) |  | Buffer day | Maple Grove Park (B+C) | Shannon Park (A)
| Arbutus Park (C) |  | Tisdall Park (A) |  |  | Oak Park (B) | Tisdall Park (A)
| Fraser River Park (C) |  | Winona Park (A) |  |  | Columbia Park (B+C) | Winona Park (A)
| Shannon Park (C) |  | Oak Meadows (A) |  |  |  | Oak Meadows (A)
|  |  | Montgomery Park (A+B) |  |  |  | Montgomery Park (A+B)
Mechanic day
22 | 23 |  | 24 |  | 25 | 26 | 27 | 28
| Eburne Park (C) |  | Shannon Park (A) |  | McCleery Park (C) | Maple Grove Park (B+C) | Shannon Park (A)
| Ash Park (C) |  | Tisdall Park (A) |  | Arbutus Park (C) | Oak Park (B) | Tisdall Park (A)
| Cambie Park (C) |  | Winona Park (A) |  | Fraser River Park (C) | Columbia Park (B+C) | Winona Park (A)
| Marpole Park (C) |  | Oak Meadows (A) |  | Shannon Park (C) |  | Oak Meadows (A)
| Winona Park (C) |  | Montgomery Park (A+B) |  | Mechanic day |  | Montgomery Park (A+B)
Tisdall Park (C)
29 | 30 |  | 31
| Eburne Park (C) |  | Shannon Park (A)
| Ash Park (C) |  | Tisdall Park (A)
| Cambie Park (C) |  | Winona Park (A)
| Marpole Park (C) |  | Oak Meadows (A)
| Winona Park (C) |  | Montgomery Park (A+B)

## Oct - Central run
| Area: | SOUTH |  | Crew Lead: | Lorri Lawson | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
OCTOBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
1 | 2 |  | 3 |  | 4 | 5 | 6 | 7
| Memorial South Park (C) |  | Hillcrest (A) |  | Buffer day | Gordon Park (B) | Hillcrest (A)
| Gordon Park (C) |  | Memorial South Park (A) |  |  | Riley Park (B) | Memorial South Park (A)
| Ross Park (C) |  | Moberly Park (A) |  |  | George Park (B) | Moberly Park (A)
| Moberly Park (C) |  |  |  |  | Ross Park (B)
Fraserview Park (C)
Mechanic day
8 | 9 |  | 10 |  | 11 | 12 | 13 | 14
| Thanksgiving Day |  | Hillcrest (A) |  | Riley Park (C) | Gordon Park (B) | Hillcrest (A)
|  |  | Memorial South Park (A) |  | Hillcrest Park (C) | Riley Park (B) | Memorial South Park (A)
|  |  | Moberly Park (A) |  | Cartier Park (C) | George Park (B) | Moberly Park (A)
[5 empty] | Grays Park (C) | Ross Park (B)
Macdonald Park (C)
Sunset Park (C)
Tecumseh Park (C)
Mechanic day
15 | 16 |  | 17 |  | 18 | 19 | 20 | 21
| Memorial South Park (C) |  | Hillcrest (A) |  | Buffer day | Gordon Park (B) | Hillcrest (A)
| Gordon Park (C) |  | Memorial South Park (A) |  |  | Riley Park (B) | Memorial South Park (A)
| Ross Park (C) |  | Moberly Park (A) |  |  | George Park (B) | Moberly Park (A)
| Moberly Park (C) |  |  |  |  | Ross Park (B)
Fraserview Park (C)
Mechanic day
22 | 23 |  | 24 |  | 25 | 26 | 27 | 28
| Riley Park (C) |  | Hillcrest (A) |  | Memorial South Park (C) | Gordon Park (B) | Hillcrest (A)
| Hillcrest Park (C) |  | Memorial South Park (A) |  | Gordon Park (C) | Riley Park (B) | Memorial South Park (A)
| Cartier Park (C) |  | Moberly Park (A) |  | Ross Park (C) | George Park (B) | Moberly Park (A)
| Grays Park (C) |  |  |  | Moberly Park (C) | Ross Park (B)
| Macdonald Park (C) |  |  |  | Fraserview Park (C)
| Sunset Park (C) |  |  |  | Mechanic day
Tecumseh Park (C)
29 | 30 |  | 31
| Riley Park (C) |  | Hillcrest (A)
| Hillcrest Park (C) |  | Memorial South Park (A)
| Cartier Park (C) |  | Moberly Park (A)
Grays Park (C)
Sunset Park (C)
Tecumseh Park (C)

## Oct - East run
| Area: | SOUTH |  | Crew Lead: | Tony Brown | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
OCTOBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
1 | 2 |  | 3 |  | 4 | 5 | 6 | 7
| Kingcrest Park (C) |  | Bobolink Park (A) |  | Buffer day | Jones Park (B) | Bobolink Park (A)
| Kensington Park (C) |  | Champlain Park (A) |  |  | Earles Park (B) | Champlain Park (A)
| Jones Park (C) |  | Killarney Park (A) |  |  | Norquay Park (B+C) | Killarney Park (A)
| Earles Park (C) |  | Kingcrest Park (A) |  |  | Nanaimo Park (B+C) | Kingcrest Park (A)
| Killarney Park (C) |  | Kensington Park (A) |  |  |  | Kensington Park (A)
Mechanic day
8 | 9 |  | 10 |  | 11 | 12 | 13 | 14
| Thanksgiving Day |  | Bobolink Park (A) |  | Sparwood Park (C) | Jones Park (B) | Bobolink Park (A)
|  |  | Champlain Park (A) |  | Captain Cook Park (C) | Earles Park (B) | Champlain Park (A)
|  |  | Killarney Park (A) |  | Rosemont Park (C) | Norquay Park (B+C) | Killarney Park (A)
|  |  | Kingcrest Park (A) |  | Humm Park (C) | Nanaimo Park (B+C) | Kingcrest Park (A)
|  |  | Kensington Park (A) |  | Riverfront Park (C) |  | Kensington Park (A)
Champlain Park (C)
Killarney Park (C)
Mechanic day
15 | 16 |  | 17 |  | 18 | 19 | 20 | 21
| Kingcrest Park (C) |  | Bobolink Park (A) |  | Buffer day | Jones Park (B) | Bobolink Park (A)
| Kensington Park (C) |  | Champlain Park (A) |  |  | Earles Park (B) | Champlain Park (A)
| Jones Park (C) |  | Killarney Park (A) |  |  | Norquay Park (B+C) | Killarney Park (A)
| Earles Park (C) |  | Kingcrest Park (A) |  |  | Nanaimo Park (B+C) | Kingcrest Park (A)
| Killarney Park (C) |  | Kensington Park (A) |  |  |  | Kensington Park (A)
Mechanic day
22 | 23 |  | 24 |  | 25 | 26 | 27 | 28
| Sparwood Park (C) |  | Bobolink Park (A) |  | Kingcrest Park (C) | Jones Park (B) | Bobolink Park (A)
| Captain Cook Park (C) |  | Champlain Park (A) |  | Kensington Park (C) | Earles Park (B) | Champlain Park (A)
| Rosemont Park (C) |  | Killarney Park (A) |  | Jones Park (C) | Norquay Park (B+C) | Killarney Park (A)
| Humm Park (C) |  | Kingcrest Park (A) |  | Earles Park (C) | Nanaimo Park (B+C) | Kingcrest Park (A)
| Riverfront Park (C) |  | Kensington Park (A) |  | Killarney Park (C) |  | Kensington Park (A)
| Champlain Park (C) |  |  |  | Mechanic day
Killarney Park (C)
29 | 30 |  | 31
| Sparwood Park (C) |  | Bobolink Park (A)
| Captain Cook Park (C) |  | Champlain Park (A)
| Rosemont Park (C) |  | Killarney Park (A)
| Humm Park (C) |  | Kingcrest Park (A)
Champlain Park (C)
Killarney Park (C)

## Oct - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
OCTOBER 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
1 | 2 | 3 |  | 4 | 5 | 6 | 7
8 | 9 | 10 |  | 11 | 12 | 13 | 14
Thanksgiving Day
15 | 16 | 17 |  | 18 | 19 | 20 | 21
22 | 23 | 24 |  | 25 | 26 | 27 | 28
29 | 30 | 31

## Nov - West run
| Area: | SOUTH |  | Crew Lead: | Coleton Fee | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
NOVEMBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[5 empty] | 1 | 2 | 3 | 4
5 | 6 |  | 7 |  | 8 | 9 | 10 | 11
Unscheduled Month
12 | 13 |  | 14 |  | 15 | 16 | 17 | 18
Remembrance Day Stat
19 | 20 |  | 21 |  | 22 | 23 | 24 | 25
26 | 27 |  | 28 |  | 29 | 30

## Nov - Central run
| Area: | SOUTH |  | Crew Lead: | Lorri Lawson | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
NOVEMBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[5 empty] | 1 | 2 | 3 | 4
5 | 6 |  | 7 |  | 8 | 9 | 10 | 11
Unscheduled Month
12 | 13 |  | 14 |  | 15 | 16 | 17 | 18
Remembrance Day Stat
19 | 20 |  | 21 |  | 22 | 23 | 24 | 25
26 | 27 |  | 28 |  | 29 | 30

## Nov - East run
| Area: | SOUTH |  | Crew Lead: | Tony Brown | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
NOVEMBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[5 empty] | 1 | 2 | 3 | 4
5 | 6 |  | 7 |  | 8 | 9 | 10 | 11
Unscheduled Month
12 | 13 |  | 14 |  | 15 | 16 | 17 | 18
Remembrance Day Stat
19 | 20 |  | 21 |  | 22 | 23 | 24 | 25
26 | 27 |  | 28 |  | 29 | 30

## Nov - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
NOVEMBER 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
|  |  |  | 1 | 2 | 3 | 4
5 | 6 | 7 |  | 8 | 9 | 10 | 11
12 | 13 | 14 |  | 15 | 16 | 17 | 18
Remembrance Day Stat
19 | 20 | 21 |  | 22 | 23 | 24 | 25
26 | 27 | 28 |  | 29 | 30

## Dec - West run
| Area: | SOUTH |  | Crew Lead: | Coleton Fee | Fleet equipment ID: |  |  | Back to Contents
| Section: | WEST RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
DECEMBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[7 empty] | 1 | 2
3 | 4 |  | 5 |  | 6 | 7 | 8 | 9
Unscheduled Month
10 | 11 |  | 12 |  | 13 | 14 | 15 | 16
17 | 18 |  | 19 |  | 20 | 21 | 22 | 23
24 | 25 |  | 26 |  | 27 | 28 | 29 | 30
| Christmas Day |  | Boxing Day
31

## Dec - Central run
| Area: | SOUTH |  | Crew Lead: | Lorri Lawson | Fleet equipment ID: |  |  | Back to Contents
| Section: | CENTRAL RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
DECEMBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[7 empty] | 1 | 2
3 | 4 |  | 5 |  | 6 | 7 | 8 | 9
Unscheduled Month
10 | 11 |  | 12 |  | 13 | 14 | 15 | 16
17 | 18 |  | 19 |  | 20 | 21 | 22 | 23
24 | 25 |  | 26 |  | 27 | 28 | 29 | 30
| Christmas Day |  | Boxing Day
31

## Dec - East run
| Area: | SOUTH |  | Crew Lead: | Tony Brown | Fleet equipment ID: |  |  | Back to Contents
| Section: | EAST RUN |  | Turf grades: | A, B, C
| Crew type: | WAM
DECEMBER 2017
SUN | MON |  | TUE |  | WED | THU | FRI | SAT
[7 empty] | 1 | 2
3 | 4 |  | 5 |  | 6 | 7 | 8 | 9
Unscheduled Month
10 | 11 |  | 12 |  | 13 | 14 | 15 | 16
17 | 18 |  | 19 |  | 20 | 21 | 22 | 23
24 | 25 |  | 26 |  | 27 | 28 | 29 | 30
| Christmas Day |  | Boxing Day
31

## Dec - Blank
| Area: |  | Crew Lead: |  | Fleet equipment ID: |  |  | Back to Contents
| Section: |  | Turf grades:
Crew type:
DECEMBER 2017
SUN | MON | TUE |  | WED | THU | FRI | SAT
[6 empty] | 1 | 2
3 | 4 | 5 |  | 6 | 7 | 8 | 9
10 | 11 | 12 |  | 13 | 14 | 15 | 16
17 | 18 | 19 |  | 20 | 21 | 22 | 23
24 | 25 | 26 |  | 27 | 28 | 29 | 30
| Christmas Day | Boxing Day
31

## Daily Time Card-South
PARKS OPERATIONS - DAILY TIMESHEET - SOUTH AREA
TIME ENTRY | [7 empty] | WORK RECORD | [5 empty] | Back to Contents
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6
WORKSITE #: |  |  | A) LOCATION:
B) ACTIVITY:
YEAR ____ MONTH ____ DAY ____ |  |  | C) CAUSE (for unfinished work):
D) ORDER #:
INITIAL | PERS. NUMBER | NAME | ACT. TYPE (P#) * | ABS / ATT CODE | PAY SCALE GROUP (GR-) * | LEVEL | PREM# | HOURS | HOURS | HOURS | HOURS | HOURS | HOURS
EQUIP. NUMBER |  | VEHICLE / EQUIPMENT TYPE | [5 empty] | RUN HOURS | RUN HOURS | RUN HOURS | RUN HOURS | RUN HOURS | RUN HOURS
*Please fill in Activity Type & Pay Scale Group ONLY if employee is to be paid HIGHER than their base rate.
X
| Signature - Crew Leader | [7 empty] | Signature - Superintendent
Daily Comments

## Timesheet codes-South
| Code Dictionary |  |  |  |  | Back to Contents
A) Location codes |  | B) Activity codes |  | C) Cause codes
SOUTH |  | TURF |  | WI | Weather interference
|  | MT | Mowing, trimming & leaf mulching | TR | Meetings/training
|  | TF | Turf mainenance / renovation | SA | Sanitation
|  | IR | Irrigation | EV | Events/crowds in park
|  | DM | Diamond maintenance | EB | Equipment breakdown
|  | AM | All weather surface maintenance | EU | Equipment unavailability
|  | ST | Synthetic turf maintenance | SU | Staff unavailability
|  |  |  | HS | Health/safety
|  | HORTICULTURE |  | OM | Other maintenance work
|  | AN | Annual & vegetable bed maintenance
|  | PE | Perennial bed maintenance
|  | RO | Rose bed maintenance
|  | SR | Shrub maintenance (regular & ground cover)
|  | NA | Naturalized maintenance
OTHER
|  | IN | Inspection (Use if no other work was required)
|  | IP | IPM
|  | DR | Debris removal & paperpicking
|  | SN | Snow removal
|  | SD | Storm clean up
|  | BM | Beach maintenance
|  | TM | Tree maintenance
|  | TR | Trail renovation/maintenance
|  | SP | Sport court cleaning
|  | WA | Pond and Water maintenance
|  | EV | Events (eg FOL)
|  | SS | Shipwreck salvage
|  | UF | Urban Forestry
|  | PH | Parking and hard surfaces
|  | AD | Administration
|  | MI | Misc. work
BLOEDEL & SUNSET NURSERY
|  | BC | Bloedel work
|  | NU | Nursery work
CITY-WIDE AREAS
XD | Destination area
XN | North area
XQ | QE, VanDusen, Bloedel, Sunset nursery
XS | South area
XW | West area

## Timesheet Definitions
TIMESHEET TERMS & DEFINITIONS
Back to Contents
MAIN TERMS
LOCATIONS |  | Locations are parks or city contracts where maintenance work is performed by Park Operations on an ongoing basis. Locations worked are tracked daily against staff hours on the timesheet.
ACTIVITIES |  | Activities are regular maintenance work that are tracked daily against staff hours on the timesheets.
CAUSE CODES |  | Cause codes are reasons for an inability to keep on schedule. We’re not measuring the time taken for cause codes, just flagging what contributed to schedule delays in order to identify and remediate these in the future.
EQUIPMENT |  | For the purposes of timesheet completion, only large equipment needs to be filled in. Large equipment includes motorized fleet vehicles, tractors and ride on mowers.
ACTIVITY DESCRIPTIONS
TURF
MT | Mowing, trimming, leaf mulching | Any mowing, trimming, or leaf mulching activity.
TF | Turf maintenance / renovation | Turf maintenance and renovation activities, including, fertilizing, liming (and soil analysis), aerating, top dressing, overseeding, verti cut dethatcher , repairing, edging and fencing.
IR | Irrigation | Any irrigation work including, marking heads, inspections, maintenance and any repairs on irrigation components. This involves both manual and automated systems.
DM | Diamond maintenance | Maintenance work on baseball diamonds, backstops, dugouts, basepads, running pads, and skinned out diamonds. Also includes edging and levelling out low spots. reinstall diamond area turf, sub soil material, irrigation (if applicable), and realign configuration of diamond to spec.
AM | All weather surface maintenance | Any work related to all weather surface fields including the use of a steel float.
SYNTHETIC TURF
ST | Synthetic turf maintenance | Maintenance work on synthetic turf fields including Vac/Blow manual, power sweeping, tow behind blower, weeding, hand grooming, infill topping.
HORTICULTURE
AN | Annual & vegetable bed maintenance | Any work on annual plant displays, including vegetables.
PE | Perennial bed maintenance | Any work on perennials plan display.
RO | Rose maintenance | Any work on formal rose beds .
SR | Shrub maintenance | Any work on shrub beds.
NA | Naturalized maintenance | Work in natural areas (natural state park).
OTHER
IP | IPM | Any work related to integrated pest management monitoring, documenting and control.
IN | Inspection (only used if no other work was required) | Inspect area to determine what, if any, work is required, and how urgent the need is for maintenance/repair.
DR | Debris removal | Paperpicking and collecting garbage/debris on a field or bed.
SN | Snow removal | Snow and ice control.
SD | Storm clean up | Green waste removal, such as broken branches and leaves, following a storm.
BM | Beach maintenance | Maintenance work on beaches.
TM | Tree maintenance | Small tree culture and low branching work on trees.
TR | Trail renovation/maintenance | Maintenance work and repair on trails and pathways, including trail vegetation maintenance.
SP | Sport court cleaning | Cleaning/weeding of hard surface sport courts.
WA | Pond and Water maintenance | Any work on bodies of water, non-chlorinated, non-recreational.
EV | Events (eg. FOL) | Non turf/hort work related to event setup/takedown.
SS | Shipwreck salvage | Removing shipwreck debris.
UF | Urban Forestry | Urban forestry work (Picking up large wood pieces on city streets and parks as a result of tree removal).
PH | Parking and hard surfaces | Maintenance work on parking lots and hard surfaces, including blowing, weeding and sweeping.
AD | Administration | Office work not directly related to a specific maintenance activity.
MI | Misc. work | Any activities that fall outside all other existing activity codes.
BLOEDEL & SUNSET NURSERY
BC | Bloedel work | Work performed at Bloedel Conservatory.
NU | Nursery work | Work performed at Sunset Nursery.
CAUSE CODES
WI | Weather interference | Weather conditions interfering with the timely adherence to the regular maintenance schedule.
TR | Meetings/training | Special meetings or training interfering with the timely adherence to the regular maintenance schedule.
SA | Sanitation | Excessive debris removal or issues with City sanitation services interfering with the timely adherence to the regular maintenance schedule.
EV | Events/crowds in park | Events or crowds of people in parks interfering with the timely adherence to the regular maintenance schedule.
EB | Equipment breakdown | Equipment breakdown interfering with the timely adherence to the regular maintenance schedule.
EU | Equipment unavailability | Equipment not available in your yard or to your crew when it is needed, interfering with the timely adherence to the regular maintenance schedule.
SU | Staff unavailability | Staff absenteeism interfering with the timely adherence to the regular maintenance schedule.
HS | Health/safety | A health concern or a safety risk interfering with the timely adherence to the regular maintenance schedule.
OM | Other maintenance work | Any other maintenance work that was unplanned or not resourced correctly, resulting in an inability to keep to the regular maintenance schedule.

## Maintenance standard
Back to Contents
WAM maintenance standard: visual criteria and maintenance frequency
Category | Visual Criteria | [15 empty] | Mowing
Activity | Grass length |  | Root depth |  | Bare ground |  | Weed tolerance |  | Turf health |  | Surface consistency |  | Drainage |  | Cutting height |  | Wide area mower |  | Leaf mulching
Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season | Growing Season | Non-Growing Season
Metric | Centimetres |  | Centimetres |  | % of ground cover |  | % of ground cover |  | a) green & healthy b) chlorotic c) heat stressed d) dormant |  | Surface consistency |  | Max. hours to 100% field perculation (no standing water) (once rain stops) |  | Centimetres |  | - | - | - | -
Grade A (Soil) | 7 - 8 cm | 7 - 8 cm | 5 - 10 cm | 5 - 10 cm | < 1% | < 1% | < 5% | < 5% | a) green & healthy | a) green & healthy | < 10 cm rise/fall over 5 m | < 10 cm rise/fall over 5 m | 2 hours | 2 hours | 6.5 cm | 6.5 cm | Twice/week | As needed | n/a | As required (weekly)
Grade A (Sand) | 7 - 8 cm | 7 - 8 cm | 10 - 15 cm | 10 - 15 cm | < 0.5% | < 0.5% | < 5% | < 5% | a) green & healthy | a) green & healthy | < 10 cm rise/fall over 5 m | < 10 cm rise/fall over 5 m | 1 hour | 1 hour | 6.5 cm | 6.5 cm | Twice/week | As needed | n/a | As required (weekly)
Grade B (Regulation, non-irrigated) | 7 - 8 cm | 7 - 8 cm | 5 - 10 cm | 5 - 10 cm | < 1% | < 1% | < 10% | < 10% | a) green & healthy or d) dormant | a) green & healthy,or d) dormant | < 10 cm rise/fall over 5 m | < 10 cm rise/fall over 5 m | 2 hours | 2 hours | 6.5 cm | 6.5 cm | Weekly | As needed | n/a | As required (weekly)
Grade C (non-regulation, non-irrigated) | 10 - 12 cm | 10 - 12 cm | n/a | n/a | < 2% | < 2% | < 20% | < 20% | a) green & healthy or d) dormant | a) green & healthy,or d) dormant | Surface is easy to mow: No tripping hazards | Surface is easy to mow: No tripping hazards | n/a | n/a | 6.5 cm | 6.5 cm | Every 10 working days | As needed | n/a | Every 3 weeks
Meadows | 15 - 60 cm | 15 - 60 cm | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 10 cm | 10 cm | Once (Mar) | Once (Aug) | n/a | n/a
Note on F8: Ron Boaz: subject to degree of unpermitted field usage
Note on G8: Ron Boaz: subject to degree of unpermitted field usage

## Area map
Back to Contents

## Principles
Back to Contents
Scheduling principles
| 1 | Schedules are future state, using the maintenance standard as the guide and not being constructed by current resource levels.
| 2 | Crew runs are balanced such that the number of A and B fields in each run is approximately equal.
| 3 | 6 hours of machine run time per day is expected.
| 4 | A and B fields are scheduled first, with grade C turf scheduled around the sports fields.
| 5 | A and B fields are scheduled primarily on Tuesdays and Fridays, and the remainder of turf on Mondays, Wednesdays, Thursdays.
| 6 | Time for equipment maintenance is built into the schedules, allowing 2-3 hours per week for this work.
| 7 | Equipment maintenance is staggered between areas to allow the mechanic to get to each yard. West on Mondays, Destination on Tuesdays, South on Wednesdays, North on Thursdays.
| 8 | 1 day of buffer is allocated every 10 working days to mitigate equipment breakdowns, weather considerations and other interruptions that may occur, in order to keep crews consistently on schedule.
| 9 | A reactive fly squad exists in the future state to deal with 311 complaints and other reactive issues, to allow park maintenance crews to keep to their schedules.
| 10 | Grade A or B turf that is not sports field turf does not need to be treated like a sports field with twice/week cutting.

## Definitions
Back to Contents
Park turf types
| 1 | Grade A (soil) | Soil based grass fields. Game fields for sports, or well manicured grass in high profile parks. Irrigated.
| 2 | Grade A (sand) | Sand based grass fields. Game fields for sports, or well manicured grass in high profile parks. Irrigated.
| 3 | Grade B | Soil based grass fields. Practice fields for sports. Non-irrigated.
| 4 | Grade C | Soil based grass areas. Infrequent maintenance. Non-irrigated.
| 5 | Meadows | Unmaintained grass areas. Cut at 4-6 inches in height. Non-irrigated.
| 6 | Synthetic Turf | Synthetic turf fields.
| 7 | Gravel | Gravel fields.
| 8 | Cinder | Legacy running track base.
| 9 | Baseball Diamond (pads) | Diamond with all grass infields.
| 10 | Baseball Diamond | Diamond with grass infield and gravel base paths.
| 11 | Softball Diamond | Diamond with all gravel infields (softball).
| Category |  | Maintenance Activity | Maintenance Activity Description
| 1 | Mowing | Wide area Mower | Ride on Mower that cuts larger areas, including sports fields and passive areas. Up to 16' wide.
|  |  | 60-72" ride on mower | Small ride on mower that is towed on a trailer or independently operated from park to park. Used for smaller areas to cut grass that is not accessible by the big mower. Often follows the wide area mower as a clean up crew.
|  |  | Trimming | Manual operation of the line trimmer/hand mower to cut grass along sidewalk edges, around benches and trees and anywhere else the mower can't get close enough to.
|  |  | Leaf Mulching | Mulching of leaves in parks where volumes are light enough to allow mulching without being detrimental to turf growth or unsightly. This operation is done by all grass mowers.
| 2 | Turf Amendment | Fertilizing | Fertilization of sports fields and premier turf to maintain proper growth of plant material. Applications vary on what the growing median is, sand or soil, and ranges from 2 - 5 times per year.
|  |  | Lime (and soil analysis) | Liming occurs after a soil analysis is done. Lime is used to adjust the pH of the soil in order for nutrients from fertilization to be available to the grass plant. Application rates are specific depending on how much the pH needs to be changed.
|  |  | Aeration: Rapid Core/core harvest | The rapid core, a 3 point attachment on a tractor, punches out small pieces of the thatch layer to allow better flow of nutrients and water to penetrate the surface and be available to the plant. The holes are punched at a very high frequency, every 3-4 ". The thatch cores are then collected by the core harvester that is a tow behind attached to a tractor. This is done to prevent a layer of thatch to develop causing the turf to be weak and water logged. Used on sand based fields where compaction is not an issue. Sand is added by topdressing, as in the vertidrain process and then dragged. The dragging also fills in low areas of the field to create a smoother, safer playing surface.
|  |  | Aeration: Vertidrain | This unit is a 3 point attachment on a tractor that is used to aerate soil based fields where compaction and poor drainage is an issue. This process is usually used in conjunction with a topdressing of sand, applied by a tractor pulling a sand spreader. This is done to create columns of sand thus increasing the movement of air, water and fertilizer in to the root zone. These fields are dragged with a drag mat pulled by a tractor to increase the efficiency of getting the sand into the columns. The dragging also fills in low areas of the field to create a smoother, safer playing surface.
|  |  | Aeration: Tow Behind | Used to aerate passive areas and B Fields. Towed behind a tractor. Used as a quick process to get to areas not normally aerated through other means. Helps reduce compaction and allows for increased drainage. Encourages healthy growth.
|  |  | Top Dress | This unit is a tow behind by a tractor. It is used to spread sand on a field during the aeration process. The sand fills the opening made by the aerator, thus increasing nutrient and water flow creating healthier turf. Once dragged in it also helps level the playing surface.
|  |  | Overseed | Unit is a 3-point attachment for a tractor. It cuts grooves into the surface and deposits seed onto the playing field. The overseeding process helps fill in bare patches, and has turf grow into areas with winter damage, and high damaged surfaces.
|  |  | Irrigation | The intentional controlled application of water to turf to promote a healthy, vigorous, sustainable stand of turf. This involves marking heads, inspections, maintenance and any repairs on irrigation components. This involves both manual and automated systems.
|  |  | Verti cut dethatch weed control | This process uses a tow behind unit for a tractor. Process is used to control thatch and weeds in turf areas. Decreasing thatch allows for a healthier turf and better water and nutrient availability. This is important because we do not use herbicides to control weeds.
| 3 | Inspection | Vandalism dog hole wear | Inspections on a weekly basis to ensure safety of the field and update field status page on the City Website. Regular inspections to complete repairs as necessary. This also applies to vehicle damage and tire ruts.
| 4 | Repair | Filling Holes | This repair work is identified through regular inspections. Examples are dog damage, field usage, and vehicular vandalism/damage.
|  |  | Wear Spots | Replacing turf surface on damaged areas to maintain consistent surface either by seeding or returfing.
|  |  | Edging | Any edging required in a park. This is done around any hard surface that grass encroaches upon. Examples: Benches, sidewalks, picnic table, and litter carts.
| 5 | Paper Pick | Debris removal | Picking up of garbage/debris on a field. Debris removal is done before any maintenance on a field. This prevents garbage from being shredded and dispersed through-out the area.
| 6 | Grooming (synthetic turf) | Vac/ Blow manual | Blowing of sidewalks and synthetic turf areas completed by backpack blowers. This is also for blowing leaves and grass clippings off hard surfaces to prevent slipping hazards, keep organic debris off the field, as well as to create a groomed appearance.
|  |  | Vac/Blow (power sweeping) | Unit is a tow behind for tractor. Grooms, vaccuums debris, and loosens infill to restore the carpet pile. (Infill Grooming Machine)
|  |  | Blower | Tow behind unit, For blowing leaves and small debris from field surface.
|  |  | Weed Control (Weeding & Moss removal) | Prong rake is used to weed at the interface between the synthetic grass and the perimeter curb. If necessary, biodegradable weed killer is used to treat the area.
|  |  | Groom Machine (Brush Sweeper) | Tow behind 3 point hitch attached brush with rows of tine brush used to agitate exposed fibres and to groom top layer of the infill. This process prevents the exposed grass fibers from matting down and loosens infill to optimize drainage. (Every six weeks).
|  |  | Groom Hand | Hand groomer (walk-behind) does edges that large machines can't get to. The groomer contains a magnet to pick up metallic objects, filter biological debris, agitate exposed fibres and groom the top layer of the infill. This process prevents the exposed grass fibers from matting down and loosens infill to optimize drainage.
|  |  | Infill Topping | This process uses a manual stiff bristle brush and garden rake to agitate the exposed fibers. Pre-mixed infill is then applied and distributed evenly over the area.
|  |  | Power Sweeper | Tow behind power-take-off-driven unit, combs the turf surface in order to remove debris such as sunflower seeds, metal, loose debris and other organic debris. The unit is equipped with tines, brush, vacuum, magnetic roller and a mesh for screening and separating rubber infill and dropping the infill back down into the carpet.
| 7 | Grooming | Pre-Season Diamond Preparation | Physically remove all weeds from aggregate around backstops, dugouts, basepads, running pads, and skinned out diamonds. Also includes edging and levelling out low spots.
| 8 | All weather surface | Re-grade (all weather surface) | Use of a steel float that is towed/dragged behind a tractor or truck. This unit levels, grades, and reduces weed growth.
| 9 | Re-Build | Diamond Re-Build | Tear out existing diamond, reinstall diamond area turf, sub soil material, irrigation (if applicable), and realign configuration of diamond to spec.
| 10 | IPM | IPM | A systematic controlled approach that utilizes a variety of least disruptive techniques in order to reduce pest damage or unwanted vegetation to thresholds of tolerable levels. Methods include a combination of physical, cultural, biological and chemical methods chosen for the most effective, safe and economical control of pests and diseases. Synthetic pesticides should be used as a last resort.

## Asset Info - West run
Back to Contents
Park asset information
| A + PN + A + T + XX = asset ID reference |  | Area: | SOUTH
| Area | (A) | Section: | WEST RUN
| Park name | (PN) | Crew type: | WAM
| Asset | (A)
| Type | (T)
| Sequential number | (XX)
| Location | Park Code | Asset ID(s) | Grade A (Soil) | Grade A (Sand) | Grade B f | Grade C f
| Arbutus Park | AR | SARTC01 | - | - | - | 9126.8291
| Ash Park | AS | SASTC01 | - | - | - | 4965.0721
| Cambie Park | CM | SCMTC01 | - | - | - | 10465.0844
| Columbia Park | CZ | SCZTB01 | - | - | 16573.8342 | -
|  | CZ | SCZTC01 | - | - | - | 10204.38
| Eburne Park | EU | SEUTC01 | - | - | - | 7274.5566
| Fraser River Park | FR | SFRTB01 | - | - | 6884.2835 | -
|  | FR | SFRTC01 | - | - | - | 36971
| Maple Grove Park | MV | SMVTA01 | 998.2884 | - | - | -
|  | MV | SMVTB01 | - | - | 3589.9167 | -
|  | MV | SMVTC01 | - | - | - | 32079.6585
| Marpole Park | MR | SMRTC01 | - | - | - | 2714.8305
| McCleery Park | MC | SMCTC01 | - | - | - | 3736.9649
| Montgomery Park | MM | SMMTA01 | 19836.6784 | - | - | -
|  | MM | SMMTB01 | - | - | 17388.9204 | -
|  | MM | SMMTC01 | - | - | - | 5737.1781
| Oak Meadows Park | OM | SOMTA01 | - | 9460.3865 | - | -
|  | OM | SOMTC01 | - | - | - | 29345.5349
| Oak Park | OA | SOATB01 | - | - | 15552.5769 | -
|  | OA | SOATC01 | - | - | - | 20459.1287
| Riverview Park | RV | SRVTC01 | - | - | - | 24528.2667
| Shannon Park | SH | SSHTA01 | 7147.0709 | - | - | -
|  | SH | SSHTC01 | - | - | - | 3333.9101
| Tisdall Park | TI | STITA01 | 16267.7579 | - | - | -
|  | TI | STITC01 | - | - | - | 30359.3489
| Winona Park | WN | SWNTA01 | 26402.2508 | - | - | -
|  | WN | SWNTC01 | - | - | - | 29322.1131
|  | Totals: | - | 70652.0464 | 9460.3865 | 59989.5318 | 260623.8564

## Asset Info - Central run
Back to Contents
Park asset information
| A + PN + A + T + XX = asset ID reference |  | Area: | SOUTH
| Area | (A) | Section: | CENTRAL RUN
| Park name | (PN) | Crew type: | WAM
| Asset | (A)
| Type | (T)
| Sequential number | (XX)
| Location | Park Code | Asset ID(s) | Grade A (Soil) | Grade A (Sand) | Grade B f | Grade C f
| Cartier Park | CT | SCTTC01 | - | - | - | 3383
| Fraserview Park | FV | SFVTB01 | - | - | 2164.3072 | -
|  | FV | SFVTC01 | - | - | - | 5801.3619
| George Park | GE | SGETC01 | - | - | - | 15190.1359
| Gordon Park | GO | SGOTB01 | - | - | 43666.2304 | -
|  | GO | SGOTC01 | - | - | - | 18656.4843
| Grays Park | GY | SGYTC01 | - | - | - | 11170.6016
| Hillcrest Park | HP | SHPTA01 | - | 38618.1738 | - | -
|  | HP | SHPTC01 | - | - | - | 51423.3217
| MacDonald Park | MD | SMDTC01 | - | - | - | 9942.4787
| Memorial South Park | MS | SMSTA01 | 18405.1561 | 12143.0047 | - | -
|  | MS | SMSTC01 | - | - | - | 69067.7904
| Moberly Park | MO | SMOTA01 | 16554.2998 | - | - | -
|  | MO | SMOTC01 | - | - | - | 18558.5532
| Nat Bailey Stadium Park | NS | SNSTC01 | - | - | - | 13642.6911
| Riley Park | RI | SRITB01 | - | - | 4075.2801 | -
|  | RI | SRITC01 | - | - | - | 7240.9488
| Ross Park | RS | SRSTB01 | - | - | 6772.01 | -
|  | RS | SRSTC01 | - | - | - | 8340.9068
| Sunset Park | SE | SSETB01 | - | - | 10064.8967 | -
| Sunset Park | SE | SSETC01 | - | - | - | 26190.03
| Tecumseh Park | TE | STETC01 | - | - | - | 18547.1401
|  | Totals: | - | 34959.4558 | 50761.1785 | 66742.7243 | 277155.4445

## Asset Info - East run
Back to Contents
Park asset information
| A + PN + A + T + XX = asset ID reference |  | Area: | SOUTH
| Area | (A) | Section: | EAST RUN
| Park name | (PN) | Crew type: | WAM
| Asset | (A)
| Type | (T)
| Sequential number | (XX)
| Location | Park Code | Asset ID(s) | Grade A (Soil) | Grade A (Sand) | Grade B f | Grade C f
| Bobolink Park | BO | SBOTA01 | 15494.9694 | - | - | -
|  | BO | SBOTB01 | - | - | 2851.8646 | -
|  | BO | SBOTC01 | - | - | - | 16727.5242
| Captain Cook Park | CC | SCCTC01 | - | - | - | 16514.0232
| Champlain Heights Park | CH | SCHTA01 | 7369.757 | - | - | -
|  | CH | SCHTC01 | - | - | - | 12212.908
| Earles Park | EA | SEATB01 | - | - | 5806.1632 | -
|  | EA | SEATC01 | - | - | - | 10662.639
| Humm Park | HU | SHUTC01 | - | - | - | 2616.5117
| Jones Park | JO | SJOTB01 | - | - | 4007.0682 | -
|  | JO | SJOTC01 | - | - | - | 7810.0536
| Kensington Park | KE | SKETA01 | - | 15821.7343 | - | -
|  | KE | SKETC01 | - | - | - | 29649.9051
| Killarney Park | KI | SKITA01 | 23091.6914 | - | - | -
|  | KI | SKITC01 | - | - | - | 77614.1019
| Kingcrest Park | KN | SKNTA01 | 7936 | - | - | -
|  | KN | SKNTC01 | - | - | - | 15029.8909
| Nanaimo Park | NA | SNATB01 | - | - | 12521.7817 | -
|  | NA | SNATC01 | - | - | - | 13203.4088
| Norquay Park | NO | SNOTB01 | - | - | 8829.6459 | -
| Norquay Park | NO | SNOTC01 | - | - | - | 11538.7179
| Riverfront Park | RF | SRFTA01 | 10251.1099 | - | - | -
|  | RF | SRFTC01 | - | - | - | 17888.8649
| Rosemont Park | RM | SRMTC01 | - | - | - | 4915.7099
| Sparwood Park | SW | SSWTB01 | - | - | 4966.6996 | -
|  | SW | SSWTC01 | - | - | - | 25830.368
|  | Totals: | - | 64143.5277 | 15821.7343 | 38983.2232 | 262214.627